## Instructions
ITRCC ERP
Requirements Conformance Matrix
Instructions to complete the HUB Requirements Conformance Matrix Worksheet
Columns A and B: The Requirement Number and Requirement coincide with the RFP Appendix A-ERP Requirements and Appendix B- Statement of Work
Column C: Defines as B-Base Product included without modification, M-Base Modified requires configuration changes and D-New Development is new code development or integration to new products and E-Exception where the functionality is not provided.
Column D: Enter in the drop down list "YES" or "NO" that your solution meets the requirement.
Column E: Proposer describes it solution and how it will meet the requirements. The proposer shall identify any additional functionality provided or exceptions.

## Conformance Matrix
Requirement Number | Requirement | Function | Phase | B-Base Product M-Base Modified D-New Development E-Exception | Meets Requirement (YES/NO) | Technical Reply
ERP-GEN-1 | The ERP solution shall provide business hours support services. The Proposer shall outline its support services in its proposal. | Financials, Purchasing | Phase 1
ERP-GEN-2 | The ERP solution shall allow a maximum of at least 50 concurrent users can work in the same module simultaneously and generate reports against the same data at the same time. The proposer shall describe the scalability of their platform, and any additional costs associated with increasing or reducing resource sizes in their initial proposal. | Financials, Purchasing | Phase 1
ERP-GEN-3 | The ERP solution shall have custom filtering and drill down capability for reports from summary to transaction detail. Including but not limited to: - Monthly account GL activity for a given year - Drill down meaning the ability to double click on specific monthly debits or credits, to see detailed GL activity that sums up the debits and credits - Filter based on transaction date, account number, company code, department code, account code, and any custom coding (capex asset code, project code for capex, vendor codes, etc.) | Financials, Purchasing | Phase 1
ERP-GEN-4 | The ERP solution must support data import and export in formats compatible with Microsoft Office (Excel, CSV), JSON, and Adobe PDF. Proposers should detail bulk data handling options in their initial proposal. Key Functionalities: Data Download: Users can download data in CSV, Excel, or similar structured formats with customizable fields and filters. The system should notify users of successful download or errors and allow report previews. Report Generation: Reports must be exportable in PDF, Excel, or CSV formats, with predefined templates and customization options. Reports should support tables, charts, and text annotations while maintaining formatting integrity. Data Upload: Users can upload large datasets (up to 50,000 records) in CSV, Excel, or JSON formats through an intuitive interface. The system must validate uploaded files for correct formats before processing. Data Validation: The system checks uploaded files for errors (e.g., incorrect data types, missing fields) and provides detailed error messages. Users can download a report of validation errors and re-upload corrected files. Data Processing: Validated data is automatically stored, and users receive confirmation of processed records. Supports scheduled batch uploads for recurring data imports. Error Handling: Users receive clear error messages for failed uploads and can retry after resolving issues. File Integrity & Security: Secure upload methods (e.g., HTTPS, encryption) prevent data corruption and unauthorized access. User Feedback & Confirmation: Real-time progress indicators inform users about upload status. | Financials, Purchasing | Phase 1
ERP-GEN-5 | The ERP solution shall have an uptime of 99.95% excluding all non-planned maintenance outages. ITR desires the solution be a web‐based application system with no plugins. The proposer shall describe all dependencies required for the solution implemented including but not limited to specialized libraries, web plugins, specific network access, etc. in their initial proposal. The proposer shall describe the maximum time for all planned maintenance outages for a calendar year. | Financials, Purchasing | Phase 1
ERP-GEN-6 | The ERP solution shall have user defined fields that can be accessed through queries and reports that are grouped or aggregated as such. The proposer shall describe the availability of client-side configuration changes and provide training on necessary components. | Financials, Purchasing | Phase 1
ERP-GEN-7 | The ERP solution shall set multiple records retention schedules that trigger automatic disposition of records by schedule. The Financial solution disposal and archiving of data shall be configurable by user and module. The proposer shall describe their recommended baseline data retention in their initial proposal with a minimum requirement of 10 years of data retained. | Financials, Purchasing | Phase 1
ERP-GEN-8 | The ERP solution shall have multiple year history to be maintained separately, by year. Any changes to current year’s G/L account structure do not impact historical amounts. The proposer shall describe their data storage options including hot and cold storage in their initial proposal | Financials, Purchasing | Phase 1
ERP-GEN-9 | The ERP Solution shall have near real time processing of data through all workflows and submitted in their final state within 10 minutes upon being received by the system. The proposer shall describe their approach to data processing and base workflows provided by the solution. The Proposer shall describe near real time in its proposal for each module in its solution and describe including any limitations or exceptions to meet these near real time solutions. | Financials, Purchasing | Phase 1
ERP-GEN-10 | The ERP solution shall provide history of use name and ID has accessed, created, or modified each data entry item. The ERP solution shall provide full audit logs with at least username, access log and created/modified datetimes for at least a rolling twelve (12) months. The Proposer shall describe their audit log methodology in their initial proposal. | Financials, Purchasing | Phase 1
ERP-GEN-11 | The ERP solution shall conduct on demand searches, post transactions, and generate reports at all levels of the account structure by fiscal year, month, calendar year, or any user defined date within the market standard for search results delivery. | Financials, Purchasing | Phase 1
ERP-GEN-12 | The ERP solution performs keyword, wild card, and multiple field queries using SQL. The Proposer shall describe any variances from open source commercially available SQL and provide training in the implementation. | Financials, Purchasing | Phase 1
ERP-GEN-13 | The ERP solution shall save queries that can be made available to other users or held privately by users in the form of filters or reports. The Financial solution shall have a system administrator role that can add, create, maintain, modify and delete these queries. | Financials, Purchasing | Phase 1
ERP-GEN-14 | The ERP solution shall generate and make the downloading of custom reports from queries or system‐generated data available on an on-demand basis. Exporting capabilities will be available for multiple save formats (i.e. excel, PDF, delimited, etc.). | Financials, Purchasing | Phase 1
ERP-GEN-15 | The ERP solution shall have customizable templates for common reports and templates shall be reused accordingly. The proposer shall describe their out-of-the-box reporting and indented purpose of the reports. | Financials, Purchasing | Phase 1
ERP-GEN-16 | The ERP solution shall have report criteria selection via drop downs, queries, or pick lists, including but not limited to: - Account Number - Company code (dimension code) - Time frame (client side configurable) - Project ID - Capex Asset Type - Include descriptors of in between, contains | Financials, Purchasing | Phase 1
ERP-GEN-17 | The ERP solution shall allow reports to be viewed online inside the application client or download to excel, PDF, etc.. | Financials, Purchasing | Phase 1
ERP-GEN-18 | The ERP solution shall be capable of transferring system generated reports on a client side configurable scheduled to user defined distribution groups. | Financials, Purchasing | Phase 1
ERP-GEN-19 | The ERP solution shall directly print or save to PDF or MS Office. | Financials, Purchasing | Phase 1
ERP-GEN-20 | The ERP solution shall integrate with Microsoft Power BI, Tableau, or similar data reporting and visualization systems and ITR's Enterprise Data Management Solution via direct SQL access or API end points. The proposer shall provide all out of the box integration connectors and the process for defining custom connectors. | Financials, Purchasing | Phase 1
ERP-GEN-21 | GL reporting should have the ability to drill down all the way to REQ/PO . | Financials, Purchasing | Phase 1
ERP-GEN-22 | Allow access to custom made reports to users outside the finance team that is updated in real time but does not allow changes to categories of data shown. | Financials, Purchasing | Phase 1
ERP-GEN-23 | The ERP shall have designated user roles that allow for IT support, super business users, internal and external business users and read only users as follows: System Administrators- IT support Super Administrators - business super users that configure roles and access to the systems. Internal Business User that is allowed to perform designated applications Read only User The Proposer shall describe its roles in its proposal including provisions for these roles in a standard configuration. The Proposer shall work with the company and provide a roles-based access configuration for the ERP system within 30 calendar days after NTP. the RBAC shall be configured by designated Company Roles and used in all testing phases. | Financials, Purchasing | Phase 1
ERP-GEN-24 | The ERP System ERP system must provide users with the ability to export data and reports in Excel (xlsx, .csv) and PDF (pdf) formats. This functionality is essential for data analysis, reporting, and record-keeping, ensuring compatibility with widely used business tools. | Financials, Purchasing | Phase 1
ERP - Work Flows
ERP-WF-1 | The ERP solution shall provide a configurable electronic workflow for approvals. The proposer shall describe the out-of-the-box configuration options for both the proposer and client-side changes. | Financials, Purchasing | Phase 1
ERP-WF-2 | The ERP solution shall provide built‐in approvals for a hierarchy of workflow approvals based on ITR defined subject matter experts. The proposer shall describe their change in management and escalated approval flow in their initial proposal. | Financials, Purchasing | Phase 1
ERP-WF-3 | The ERP solution shall provide notifications for pending workflow approvals and notifications when SLAs are breached via application dashboards and email notifications. The proposer shall describe their recommended best practice for system alerting and monitoring for data workflows (manual and system). | Financials, Purchasing | Phase 1
ERP-WF-4 | The ERP solution shall allow for relocation or delegation of tasks/duties from one approver to another designated user in the case of short- or long-term absence. | Financials, Purchasing | Phase 1
ERP-WF-5 | The ERP solution shall designate thresholds at decision points in each workflow. | Financials, Purchasing | Phase 1
ERP-WF-6 | The ERP solution shall allow for comments to be added at each level of approval. | Financials, Purchasing | Phase 1
ERP-WF-7 | The ERP solution shall have a client trigger workflow to close the previous year's budget. The proposer shall describe their year-end processes in their initial proposal. | Financials, Purchasing | Phase 1
ERP-WF-8 | The ERP solution shall have an automatic workflow to open a new year's general ledger that can be scheduled by client-side configuration. The proposers shall describe their start-of-year processes in their initial proposal. | Financials, Purchasing | Phase 1
ERP Non-Functional Requirements
ERP-NFWF-1 | The ERP System shall be considered unavailable (System downtime) if performance is causing loss of functionality (the component or sub-System is unable to provide the required functionality); causing application errors for multiple (two or more) users; causing application errors for customers and preventing access by the Company, staff or customers causing application errors for customers and preventing access by the Company. | All | Phase 1,2 and 3
ERP-NFWF-2 | The ERP system will measure availability for all availability performance requirements by calculating the percentage of minutes in each calendar month the ERP is not affected by System downtime. | All | Phase 1,2 and 3
ERP-NFWF-3 | All unscheduled or unplanned maintenance events (corrective maintenance) shall be counted as System downtime. Corrective Maintenance that does not cause components or sub-Systems to be unavailable shall not be counted as System downtime. Scheduled or planned maintenance events (preventive maintenance) shall not be used to correct ERP System. | All | Phase 1,2 and 3
ERP-NFWF-4 | The ERP System shall provide capacity to support a minimum of 200 percent of the Company current users, accounts and financial transactions and data retention requirements. The data availability strategy shall be described in real time. RTO shall be within 24 hours for data in the current calendar year + last calendar year. The RTO all other years shall be within 48 hours of request by the user. RPO of the solution shall be the a maximum of 24 hours | All | Phase 1,2 and 3
ERP-NFWF-5 | The ERP system shall have a minimum of 100 concurrent users per calendar day. The ERP system shall be scaled to meet at least 200 concurrent users. The key parameters include concurrent finance users, concurrent PMO users and concurrent internal and external SCR users. Daily, Weekly and Monthly Peak Load based on the number of concurrent users and system users for the System and all external interfaces running concurrently. | All | Phase 1,2 and 3
ERP-NFWF-6 | The ERP system shall be upward compatible to allow future releases to work on the platform. Any testing or modifications to the product and interfaces required before the release must be documented, tested and approved by the Company before the release. | All | Phase 1,2 and 3
ERP-NFWF-7 | The products shall support future cloud, on-premises Hardware and Software changes without major changes to the Software defined as application changes. | All | Phase 1,2 and 3
ERP-NFWF-8 | For cloud versions in the ERP Solution, product release cycle shall include a sandbox for testing so that cloud upgrades may be tested. | All | Phase 1,2 and 3
ERP-NFWF-9 | The ERP System shall have the capability to support point and click or other simple mechanisms to upgrade configurations and updates to incorporate new releases. | All | Phase 1,2 and 3
ERP-NFWF-10 | The ERP System shall utilize public or private cloud or on-Premises solution. The Proposer shall describe its approach in its proposal to include PAAS, IAAS or SAAS solution. The Proposer shall describe all costs of its proposed solution including anticipated utilization costs of any cloud solution based on the Requirements. The Proposal shall include any assumptions for expected costs that are not included in the proposal to be paid by others, including amounts to be discussed with the Company by the selected Proposer. | All | Phase 1,2 and 3
ERP-NFWF-11 | The Solution shall implement role-based access control to restrict user permissions based on their titles within the organization. | All | Phase 1,2 and 3
ERP-NFWF-12 | The Solution shall allow for the creation of unlimited roles. | All | Phase 1,2 and 3
ERP-NFWF-13 | The Solution shall support two-factor authentication through Microsoft MFA for user logins to enhance security. | All | Phase 1,2 and 3
ERP-NFWF-14 | The Solution shall assure that all data resides within the United States (for cloud-based solutions) | All | Phase 1,2 and 3
ERP-NFWF-15 | The Solution shall integrate with the organization's Azure Single Sign-On (SSO) for centralized identity management. | All | Phase 1,2 and 3
ERP-NFWF-16 | The Solution shall support automated user provisioning and deprovisioning using Azure Enterprise Applications and SAML. | All | Phase 1,2 and 3
ERP-NFWF-17 | The Solution shall log all user access events, including authentication and administrative actions. | All | Phase 1,2 and 3
ERP-NFWF-18 | The Solution shall integrate with Blumira – the organization’s Security Information and Event Management (SIEM) systems for centralized log analysis. | All | Phase 1,2 and 3
ERP-NFWF-19 | The Solution shall retain logs for a minimum of one year to support security investigations and compliance audits. | All | Phase 1,2 and 3
ERP-NFWF-20 | The Solution shall ensure that all ERP system components are deployed in appropriate network segments for security isolation. (Non-SaaS solutions only) | All | Phase 1,2 and 3
ERP-NFWF-21 | The Solution shall provide secure configuration baselines for all connected devices and enforce these configurations using automated tools (e.g., Group Policy, Ansible). (Non-SaaS solutions only) | All | Phase 1,2 and 3
ERP-NFWF-22 | The Solution shall support scheduled maintenance windows for the installation of patches and security updates. (Non-SaaS solutions only) | All | Phase 1,2 and 3
ERP-NFWF-23 | The vendor shall apply critical patches on all system components within 30 days of release. | All | Phase 1,2 and 3
ERP-NFWF-24 | The Solution shall include a test environment to validate patches prior to production deployment. | All | Phase 1,2 and 3
ERP-NFWF-25 | The Solution shall support authenticated vulnerability scanning for all ERP-related infrastructure and devices. (Non-SaaS solutions only) | All | Phase 1,2 and 3
ERP-NFWF-26 | The Solution shall include incident recovery procedures as part of a formal Incident Response Plan. | All | Phase 1,2 and 3
ERP-NFWF-27 | The Solution shall comply with relevant security standards and regulations, such as PCI DSS, GDPR, HIPAA, NIST CSF. | All | Phase 1,2 and 3
ERP-NFWF-28 | The Solution shall enforce physical security measures for data centers and critical infrastructure. (Offsite solutions only) | All | Phase 1,2 and 3
ERP-NFWF-29 | The vendor shall supply and maintain up-to-date network, system architecture, and data flow diagrams prior to the implementation of any changes or at a minimum of once every 6 months if no implementations were made. | All | Phase 1,2 and 3
ERP-NFWF-30 | The Solution shall provide device configuration documentation for all ERP-related hardware and software. (Non-SaaS solutions only) | All | Phase 1,2 and 3
ERP-NFWF-31 | The vendor shall include alerting and tracking of End-of-Life (EOL) dates for all software and hardware components. | All | Phase 1,2 and 3
ERP-NFWF-32 | ITRCC shall define and document the technical and business owners responsible for system maintenance and support, as well as the scope of responsibilities for maintenance, repair, and recovery. | All | Phase 1,2 and 3
ERP-NFWF-32 | The vendor shall enforce secure coding practices for any custom ERP modules, including regular code reviews and both static and dynamic analysis. | All | Phase 1,2 and 3
ERP-NFWF-34 | The Solution shall support endpoint security measures for all system components devices accessing the ERP system, including the deployment Checkpoint endpoint detection and response (EDR), Blumira and Tenable agents. | All | Phase 1,2 and 3
ERP-NFWF-35 | The Solution shall provide initial training sessions for all users, covering key functionalities and features tailored to their roles (e.g., PMO Director, Project Manager, Stakeholders, IT support). | All | Phase 1,2 and 3
ERP-NFWF-36 | The Solution provider shall include a "train-the-trainer" program that equips designated users within the organization to provide training and support to their peers. | All | Phase 1,2 and 3
ERP-NFWF-37 | The Solution shall enable data recovery capabilities to restore critical data and systems in the event of a cyberattack or system failure. | All | Phase 1, 2,3
ERP-NFWF-38 | The Solution shall support up to 200 concurrent users without performance degradation. | All | Phase 1, 2,3
ERP-NFWF-39 | The Solution shall ensure that report generation takes no longer than 5 seconds for standard reports. | All | Phase 1, 2,3
ERP-NFWF-40 | The Solution shall load project dashboards within 1-2 seconds for optimal user experience. | All | Phase 1, 2,3
ERP-NFWF-41 | The Solution shall be designed to accommodate future growth, allowing for the addition of up to 1,000 projects and 200 users without requiring significant reconfiguration. | All | Phase 1, 2,3
ERP-NFWF-42 | The Solution shall maintain 99.5% uptime, excluding scheduled maintenance periods during business hours defined as Monday Through Friday 8 AM to 5 PM eastern time. | All | Phase 1, 2,3
ERP-NFWF-43 | The Solution shall provide a user notification system for scheduled downtime or maintenance. | All | Phase 1, 2,3
ERP-NFWF-44 | The Solution shall encrypt all sensitive data both in transit and at rest using industry-standard encryption protocols. | All | Phase 1, 2,3
ERP-NFWF-45 | The Solution shall support two-factor authentication through Microsoft MFA for user logins to enhance security. | All | Phase 1, 2,3
ERP-NFWF-46 | The Solution shall disable all unused ports, interfaces, and services on network-connected devices to minimize the attack surface. (Non-SaaS solutions only) | All | Phase 1, 2,3
ERP-NFWF-47 | The Solution shall enable data recovery capabilities to restore critical data and systems in the event of a cyberattack or system failure. | All | Phase 1, 2,3
ERP-NFWF-48 | The Solution shall have an intuitive user interface that requires no more than 2 hours of training for new users to become proficient. Power users including PMO director training may be longer. | All | Phase 1, 2,3
ERP-NFWF-49 | The Solution shall provide context-sensitive help and documentation accessible from any screen. | All | Phase 1, 2,3
ERP-NFWF-50 | The Solution shall integrate with existing enterprise systems within ITR through standard APIs to enable seamless data exchange. (as detailed in Integration Requirements) | All | Phase 1, 2,3
ERP-NFWF-51 | The Solution shall support data import and export in commonly used formats such as CSV, Excel, JSON, PARQUE, and XML. | All | Phase 1, 2,3
ERP-NFWF-52 | The Solution shall allow for the easy addition of new features and updates with minimal downtime. | All | Phase 1, 2,3
ERP-NFWF-53 | The Solution shall be Cloud or on-Premises but have usability models for lifecycle cost planning. The Proposer shall describe and provide its cost models and recommendations in its proposal. | All | Phase 1, 2,3
ERP-NFWF-54 | The Solution shall provide access for the ITR support team and include a logging mechanism that tracks errors and system performance for troubleshooting and maintenance purposes. | All | Phase 1, 2,3
ERP-NFWF-55 | The Solution shall comply with relevant industry standards and regulations, such as General Data Protection Regulation (GDPR) for data protection and PMI standards for project management. | All | Phase 1, 2,3
ERP-NFWF-56 | The Solution shall implement automated daily backups and provide a recovery process that ensures RPO/RTO restoration not to exceed 24 hours in the event of a system failure. | All | Phase 1, 2,3
ERP-NFWF-57 | The Solution shall have field level restrictions. | All | Phase 1, 2,3
ERP-NFWF-58 | The Solution shall maintain a comprehensive audit trail of user activities, changes made to project data, and system access for accountability and compliance purposes. | All | Phase 1, 2,3
ERP-NFWF-59 | The Solution shall comply with WCAG 2.1 (Web Content Accessibility Guidelines) to ensure usability for users with disabilities. | All | Phase 1, 2,3
ERP-NFWF-60 | The Solution shall allow users to customize dashboards and reports to meet their specific project management needs. | All | Phase 1, 2,3
ERP-NFWF-61 | The Solution provider shall provide a dedicated help desk for users to report issues, request assistance, and receive guidance during business hours (hours (hours (8:00am-5:00 pm EST) | All | Phase 1, 2,3
ERP-NFWF-62 | The Solution provider shall guarantee a response time of no more than 2 hours for critical support requests and 24 hours for non-critical issues. | All | Phase 1, 2,3
ERP-NFWF-63 | The Solution shall include an online knowledge base that provides users with FAQs, troubleshooting guides, and best practices for using the PMO solution. | All | Phase 1, 2,3
ERP-NFWF-64 | The Solution shall provide comprehensive user documentation, including user manuals, quick start guides, and reference materials accessible from within the application that are updated at the time of implementation and confirmed by the vendor to be up to date a minimum of every 6 months. | All | Phase 1, 2,3
ERP-NFWF-65 | The Solution provider shall offer a variety of training resources, including video tutorials, webinars, and self-paced online courses to accommodate different learning styles. | All | Phase 1, 2,3
ERP-NFWF-66 | The Solution shall include a communication plan for notifying users of system updates, new features, and scheduled maintenance to ensure continued support. | All | Phase 1, 2,3
ERP-NFWF-67 | The Solution shall have a mechanism for users to submit feedback on system performance and support experiences, which will be reviewed regularly for improvement. | All | Phase 1, 2,3
ERP-NFWF-68 | The Solution provider shall offer role-specific training programs to ensure that each user group understands how to effectively utilize the features relevant to their responsibilities. | All | Phase 1, 2,3
ERP-NFWF-69 | The Solution shall provide ongoing training opportunities, including advanced courses and refresher training sessions, to keep users updated on new features and best practices. | All | Phase 1, 2,3
ERP-NFWF-70 | The Solution shall supply comprehensive training materials, including slide decks, handouts, and access to recorded sessions for future reference. | All | Phase 1, 2,3
ERP-NFWF-71 | The Solution shall implement a structured onboarding process for new users, including mentoring by experienced users or trainers during their initial usage. | All | Phase 1, 2,3
ERP-NFWF-72 | The Solution shall offer assessment tools to evaluate user knowledge and proficiency, with the option for certification upon successful completion of training programs. | All | Phase 1, 2,3
Financials - General Ledger
ERP-FIN-1 | The Financial solution shall have a chart of accounts that allows the user complete control over structure. The Financial solution shall allow for different structures for balance sheet, revenue and expenditure accounts, in addition to custom financial statement roll up fields. The proposer shall describe and provide their baseline forms and describe client-side configuration options to tailor forms to ITR's specific business need. | Financials | Phase 1
ERP-FIN-2 | The Financial solution shall support all accounting requirements related to International Financial Reporting Standards (IFRS) and Generally Accepted Accounting Principles (GAAP). These include but are not limited to: 1. Compliance and Standardization: Ability to generate financial reports following IFRS and GAAP. Support for multi-GAAP and IFRS adjustments in financial statements. Automatic application of accounting policies based on the applicable standard. 2. Chart of Accounts & Multi-Currency Support: Flexible chart of accounts to align with both IFRS and GAAP reporting needs. Multi-currency transactions with proper translation and consolidation. Exchange rate adjustments per IFRS/GAAP guidelines. 3. Revenue Recognition & Lease Accounting: Compliance with IFRS 15 / ASC 606 for revenue recognition. Proper lease accounting as per IFRS 16 / ASC 842. Deferred revenue tracking and contract management. 4. Financial Consolidation & Reporting: Consolidation of financial statements across multiple entities. Elimination of intercompany transactions. Segment and entity-level reporting. 5. Audit Trails & Internal Controls: Strong audit trail for tracking changes to financial data. User access controls to ensure segregation of duties. Automated workflows for approvals and compliance monitoring. 6. Fixed Asset & Depreciation Management: Handling of depreciation and impairment as per IAS 16 and GAAP. Asset revaluation and impairment tracking. 7. Tax & Regulatory Compliance: Automatic tax calculations aligned with IFRS and GAAP standards. Deferred tax calculations as per IAS 12 / ASC 740. Compliance with local and international tax laws. 8. Automation & Integration: Ability to integrate with ERP, payroll, procurement, and financial planning systems. Automation of journal entries, allocations, and accruals. 9. Disclosure & Notes Preparation: Support for generating required disclosures and footnotes. Customizable templates for financial statements. 10. Financial Statement Generation: Balance Sheet, Income Statement, Cash Flow Statement in both IFRS and GAAP formats. Ability to generate comparative statements. | Financials | Phase 1
ERP-FIN-3 | The Financial solution shall have controls to ensure subsystems, e.g. project/grants management, contracts management, procurement management, fixed assets, are in balance with control accounts, e.g. general ledger accounts, subsidiary accounts. The proposer shall describe their automated workflows for subsystem roll up, their suggested variance thresholds and client-side configuration of thresholds in their initial proposal. | Financials | Phase 1
ERP-FIN-4 | The system shall provide users with the capability to review results prior to posting. The solution shall enforce a review step prior to the posting of data that includes but is not limited to validating mandatory fields outlined, user acceptance of changes and notifications of errors | Financials | Phase 1
ERP-FIN-5 | The Financial solution shall allow users to upload journal entries from Microsoft Excel or other external systems. Shall also allow to upload supporting material to journal entries in PDF, excel and other formats. | Financials | Phase 1
ERP-FIN-6 | The Financial solution shall indicate the source of the transaction, e.g. manual entry or automated entry (system generated). | Financials | Phase 1
ERP-FIN-7 | The Financial solution shall allow users to record the actual posting date and the financial effective date. | Financials | Phase 1
ERP-FIN-8 | The Financial solution shall afford various views of the General Ledger within the application including but not limited to data slicers of department, project, account, etc. | Financials | Phase 1
ERP-FIN-9 | The Financial solution provides the ability to move from a G/L account to specific transactions affecting the account (drill‐down capabilities). | Financials | Phase 1
ERP-FIN-10 | The Financial solution shall conduct searches, post transactions, and generate reports at all levels of the account structure by fiscal year, month, calendar years, or any user‐ defined date. | Financials | Phase 1
ERP-FIN-11 | The Financial solution shall provide configurable business rules to prevent transactions from posting to invalid accounting combinations. The proposer shall include baseline or recommended customized client-side configuration capabilities for transaction posting validations in their initial proposal. | Financials | Phase 1
ERP-FIN-12 | The Financial solution shall support cash basis, accrual basis, year‐end accrual basis, or any combination thereof. | Financials | Phase 1
ERP-FIN-13 | The Financial solution shall allow at least 13 periods per year with open periods. A period should be defined as monthly, quarterly, annual, and fiscal years. The proposer shall describe how the client can configure and maintain periods in their initial proposal. | Financials | Phase 1
ERP-FIN-14 | The Financial solution provides the ability to lock the previous year after year‐end closure to avoid inadvertent changes. The proposer shall describe their previous year safeguards and out-of-the-box validation workflows for end-of-year reconciliation, and workflow for an escalated permission user to modify previous year financials in case of an error in their initial proposal. | Financials | Phase 1
ERP-FIN-15 | The Financial solution shall provide a system workflow for automatic journal entry reversals. | Financials | Phase 1
ERP-FIN-16 | The Financial solution shall provide automatic year‐end closing workflow while maintaining data accuracy and access to detail records for at least 12 months. The proposer shall describe the end-of-year closing workflow in their initial proposal. | Financials | Phase 1
ERP-FIN-17 | The Financial solution shall import the past 10 years 5 years to hot storage and 5 years into cold/less responsive storage of GL activity from Microsoft Great Plains and tie to audited financial statements | Financials | Phase 1
Financials - Budgeting
ERP-FIN-18 | The Financial solution shall generate a budget based on client-side configurable periods. The system should support budgeting within the tool, allowing department heads to budget within the system and aggregating to a company level | Financials | Phase 1
ERP-FIN-19 | The Financial solution shall create global configuration variables that changes workflows and thresholds in a variety of datatypes including but not limited to percentages, fixed amounts, and by a user defined formula. The proposers shall describe their client-side configuration options in their initial proposal | Financials | Phase 1
ERP-FIN-20 | The Financial solution provides version history for all budgets with statuses that include but not limited to original, amended and adopted. The proposer shall describe how new values can be added through client-side configuration changes in their initial proposal. | Financials | Phase 1
ERP-FIN-21 | The Financial solution shall be capable of having multiple years budgets active at one time. | Financials | Phase 1
ERP-FIN-22 | The Financial solution shall allow multiple departments and a minimum of 25 concurrent users, and different client-side defined permissions for functions that include but not limited to read only, manager and approver access. All users should be able to access and update their budget information simultaneously. | Financials | Phase 1
ERP-FIN-23 | The Financial solution shall be capable of integrating Payroll and Human Resource modules to support salary and benefit budgeting. This is a future requirement not to be deployed in phase 1 in 2025. | Financials | Phase 3
ERP-FIN-24 | The Financial solution shall retain a full version of budget history including but not limited to original and amended budget data. | Financials | Phase 1
ERP-FIN-25 | The Financial solution shall forecast current year budget and actual on a line‐by‐line basis and on an entire budget) based on: 1. Straight line projection 2. Percentage based on last year actual 3. Percentage based on last year budget 4. Combination of the methods above within the same budget The proposer shall describe how the above use cases are covered in their solution and involve any customization development that would be necessary to accommodate. | Financials | Phase 1
ERP-FIN-26 | The Financial solution shall save scenarios by users and allow for sharing of scenarios based on email, username and permissions level. | Financials | Phase 1
ERP-FIN-27 | The Financial solution shall create salary and benefit projections that allow: 1. Add or delete positions 2. Reclassify positions 3. Modify positions 4. Transfer positions 5. Freeze or unfreeze positions 6. Split positions 7. Change the number of authorized full time equivalent per position 8. Control the number of employees filling a position based on the authorized full-time equivalents 9. Override controls for specific position types 10. Ability to route position change requests online to various staff members for approval 12. Ability to maintain position history. 13. Percentage capitalization of employee's time | Financials | Phase 1
ERP-FIN-28 | The Financial solution shall create budget relationships between items including but not limited to salary changes automatically adjust benefits and vice versa. The Proposer shall describe how its ERP solution can identify and aggregate fringe benefits. | Financials | Phase 1
ERP-FIN-29 | The Financial solution shall enter budget adjustments in a pending status for final approval through electronic workflow. The proposer shall describe their budget adjustment and approval process in their initial proposal | Financials | Phase 1
ERP-FIN-30 | The Financial solution shall through workflows notify appropriate personnel of adjustments for approval and update to the general ledger. These notifications shall be sent through ITR's email system, the proposer shall describe all available solutions for communication with end users in its initial proposal. | Financials | Phase 1
ERP-FIN-31 | The Financial solution shall allow for the creation of one or multiple forecasts and will have the capability to show historical performance vs. budget based on account numbers. | Financials | Phase 1
Financials - Accounts Payable
ERP-FIN-32 | The Financial solution shall track aging items and other exceptions. The proposer shall describe the aging process of their solution in their initial proposal. | Financials | Phase 1
ERP-FIN-33 | The Financial solution shall provide recurring payables processing | Financials | Phase 1
ERP-FIN-34 | The Financial solution shall provide vendor discount management for prepayment or early payment options | Financials | Phase 1
ERP-FIN-35 | The Financial solution shall access vendor history by vendor name, vendor number, invoice date, check date, and BAR code | Financials | Phase 1
ERP-FIN-36 | The Financial solution shall provide vendor retainage by percentage by vendor type or invoice type. | Financials | Phase 1
ERP-FIN-37 | The Financial solution shall apply credit memos against a vendor with the ability to have that credit memo applied automatically or based on a client-side defined field. | Financials | Phase 1
ERP-FIN-38 | The Financial solution shall automatically transfer issued checks to an outstanding check register and allow users to process cleared checks, including the ability to generate outstanding check register. Clearing check shall also be cleared via bank reconciliation process or file upload. | Financials | Phase 1
ERP-FIN-39 | The Financial solution shall block duplicate invoice processing. Duplicate invoices for vendors shall notify via email and or system pop up of warning/error. | Financials | Phase 1
ERP-FIN-40 | The Financial solution shall provide multiple invoices per check if required and the option to cut one check for each invoice or one check for multiple invoices. The Proposer shall describe how many invoices per check its solution can provide in its Proposal. | Financials | Phase 1
ERP-FIN-41 | The Financial solution shall attach scanned invoices to vendor files and invoice history and allow automatic destruction of invoice images per retention schedule. | Financials | Phase 1
ERP-FIN-42 | The Financial solution shall process procurement cards (p‐cards) or credit card transactions. | Financials | Phase 1
ERP-FIN-43 | The Financial solution shall receive a file import from the bank for credit card transactions. Import files shall be client side configurable to meet multiple needs and sources. | Financials | Phase 1
ERP-FIN-44 | The Financial solution shall provide outs to commercially available laser check printing. | Financials | Phase 1
ERP-FIN-45 | The Financial solution shall provide IRS 1099 reporting requirements at invoice, invoice line item and vendor. Be able to make what type of 1099 vendors they are. | Financials | Phase 1
ERP-FIN-46 | The Financial solution shall provide EFT payment formats, e.g. wire transfers or ACH transactions to vendors and employees. | Financials | Phase 1
ERP-FIN-47 | The Financial solution shall provide positive pay file output and accommodates positive pay reconciliation. | Financials | Phase 1
ERP-FIN-48 | The Financial solution shall receive a cleared check file import from the bank to clear checks and auto payments automatically. | Financials | Phase 1
ERP-FIN-49 | The Financial solution shall have sales and use tax tracking and reporting by state by vendor and by asset. | Financials | Phase 1
ERP-FIN-50 | The Financial solution shall issue payments from multiple bank accounts. | Financials | Phase 1
ERP-FIN-51 | The Financial solution shall be able to issue Check 21 (ability to deposit checks electronically) capable/compatibility. | Financials | Phase 1
ERP-FIN-52 | The Financial solution shall issue checks/checks up from $0.01 to $99,999,9999.99 configurable user. | Financials | Phase 1
ERP-FIN-53 | The Financial solution shall batch updating of cleared A/P checks. | Financials | Phase 1
ERP-FIN-54 | The Financial solution shall allow the ability to print signatures onto the check stock and change the signature used as needed. | Financials | Phase 1
ERP-FIN-55 | The Financial solution shall allow for the reprinting of checks before they are posted if errors occur during printing. | Financials | Phase 1
ERP-FIN-56 | The Financial solution shall be able to integrate with automated AP invoice processing. | Financials | Phase 1
ERP-FIN-57 | The financial solutions shall allow are report of open payables by vendor payment preference. | Financials | Phase 1
ERP-FIN-58 | The Financial solution shall show unposted invoices in a vendor transaction look up. | Financials | Phase 1
ERP-FIN-59 | The Financial solution shall have the capability to use batch processing. Invoices should be able to be saved in batches when processed so posting dates can be selected. | Financials | Phase 1
Financials - Fixed Assets
ERP-FIN-60 | The Financial solution shall be compatible with all internationally recognized financial reporting standards (IFRS and GAAP) | Financials | Phase 1
ERP-FIN-61 | The Financial solution shall provide the following minimum information required for each capital asset: 1. Category of asset and subcategory of asset, client side defined 2. General ledger fund and asset account the asset is recorded in 3. Individual or department assigned custody of the asset 4. Acquisition information, including references to source documents and acquisition dates 5. Source of payment, such as debt, grant, free cash flow, etc. 6. Historical cost 7. Valuation adjustments 8. Name and description of asset that is sufficient to specifically define and identify the asset, including any identifying numbers or legal descriptions where applicable 9. Estimated useful life 10. Disposition information, including the date and method (such as destruction, scrap, sale, etc.) and any costs or proceeds 11. Client side defined project code | Financials | Phase 1
ERP-FIN-62 | The Financial solution shall track capitalized and non‐capitalized assets, e.g. by classification structure elements | Financials | Phase 1
ERP-FIN-63 | The Financial solution shall generate accounting entries to maintain assets, e.g. transfers, impairments, acquisitions, additions, expensing of non‐capitalized costs, depreciation, and disposals of assets. | Financials | Phase 1
ERP-FIN-64 | The Financial solution shall post to a Construction in Progress asset account. | Financials | Phase 1
ERP-FIN-65 | The Financial solution shall automatically transfer Construction in Progress asset charges to an asset account upon notification that the asset is substantially complete or has been placed in service. | Financials | Phase 1
ERP-FIN-66 | The Financial solution shall automatically create multiple fixed asset records based on a purchase order, contract, direct payment, work order, or journal entry, e.g. a contract to purchase large quantities of handheld equipment, purchase multiple vehicles via one check. | Financials | Phase 1
ERP-FIN-67 | The Financial solution shall attach supporting documentation (invoices, work history, JEs, emails, etc.) to fixed asset records, and to delete attachments in accordance with retention schedules. | Financials | Phase 1
ERP-FIN-68 | The Financial solution shall assign fixed assets to one or more funds, users, and/or locations. | Financials | Phase 1
ERP-FIN-69 | The Financial solution shall define classes and categories of fixed assets. | Financials | Phase 1
ERP-FIN-70 | The Financial solution shall track the acquisition method by asset. | Financials | Phase 1
ERP-FIN-71 | The Financial solution shall provide bar coding and QR coding of assets for physical inventory. | Financials | Phase 1
ERP-FIN-72 | The Financial solution shall generate asset depreciation postings and will post automatically to the general ledger. | Financials | Phase 1
Financials Purchasing
ERP-FIN-73 | The Financial solution shall create custom purchase order templates, custom fields/elements in a database integrated with a Source to Contract solution. | Financials, Purchasing | Phase 1
ERP-FIN-74 | The Financial solution shall allow all data from template to be modified by the user and configurable by vendor. | Financials, Purchasing | Phase 1
ERP-FIN-75 | The Financial solution shall assign a unique number to each Purchase Order (PO) | Financials, Purchasing | Phase 1
ERP-FIN-76 | The Financial solution creates COB PO letters, with ability to email POs from the form. | Financials, Purchasing | Phase 1
ERP-FIN-77 | The Financial solution shall have a digital signature file or integrate to a commercial digital signature system including but not limited to Microsoft TEAMS, Adobe, and DocuSign. | Financials, Purchasing | Phase 1
ERP-FIN-78 | The Financial solution shall track and modify vendor contact information including a history and log of changes. | Financials, Purchasing | Phase 1
ERP-FIN-79 | The Financial solution shall track purchases against BAR codes and show the remaining budget balance. | Financials, Purchasing | Phase 1
ERP-FIN-80 | The Financial solution shall track invoice numbers separate from PO numbers. | Financials, Purchasing | Phase 1
ERP-FIN-81 | The Financial solution shall track the quantity purchased and quantity received on different order numbers. | Financials, Purchasing | Phase 1
ERP-FIN-82 | The Financial solution shall add scanned invoices to PO record. | Financials, Purchasing | Phase 1
ERP-FIN-83 | The Financial solution shall allow for the adjustment of sales tax rates by vendor, jurisdiction, asset, or manually. | Financials, Purchasing | Phase 1
ERP-FIN-84 | The Financial solution shall select vendors from a pull-down box or auto fill based on characters. | Financials, Purchasing | Phase 1
ERP-FIN-85 | The Financial solution shall search for previous purchases based on the item, vendor, date, account code and PO number. | Financials, Purchasing | Phase 1
ERP-FIN-86 | The Financial solution shall provide a configuration of up to 50 departments each with their own views and ranges of numbers. | Financials, Purchasing | Phase 1
ERP-FIN-87 | The Financial solution shall track purchased items as assets with a user defined asset number | Financials, Purchasing | Phase 1
ERP-FIN-88 | The Financial solution shall attach electronic documents to requisitions and purchase orders and to purge attachments in accordance with retention schedules. | Financials, Purchasing | Phase 1
ERP-FIN-89 | The Financial solution shall provide electronic routing of purchase orders for approval. | Financials, Purchasing | Phase 1
ERP-FIN-90 | The Financial solution shall track requisitions and allow for configurable multiple approval levels. | Financials, Purchasing | Phase 1
ERP-FIN-91 | The Financial solution shall provide selections of how a vendor would like to be paid. | Financials, Purchasing | Phase 1
ERP-FIN-92 | The Financial solution shall allow users to record receiving date and approvals for payment; integrates with the Financials Solution. | Financials, Purchasing | Phase 1
Financial Multicompany Reporting
ERP-FIN-93 | The Financial solution must support financial reporting for multiple legal entities within a single platform and allow for real-time aggregation to configurable parent companies. | Financials | Phase 1
ERP-FIN-94 | The Financial solution shall allow users to generate entity-specific and consolidated financial statements. | Financials | Phase 1
ERP-FIN-95 | The Financial solution system should be able to support multiple currencies and apply appropriate exchange rate conversions. | Financials | Phase 1
ERP-FIN-96 | The Financial solution must generate financial statement consolidation at multiple levels (e.g., subsidiary, regional, group level). | Financials | Phase 1
ERP-FIN-97 | The Financial solution should automate the consolidation process, applying appropriate accounting standards (GAAP, IFRS, etc.). | Financials | Phase 1
ERP-FIN-98 | The Financial solution should allow for real-time or scheduled consolidation runs. | Financials | Phase 1
ERP-FIN-99 | The Financial solution must automatically identify and eliminate intercompany transactions | Financials | Phase 1
ERP-FIN-100 | The Financial solution should support various elimination scenarios, including revenue, expenses, receivables, payables, assets and debt between entities. | Financials | Phase 1
ERP-FIN-101 | The Financial solution shall allow users to be able to configure elimination rules and exceptions. | Financials | Phase 1
ERP-FIN-102 | The Financial solution shall provide a detailed audit trail to be maintained for all intercompany eliminations. | Financials | Phase 1
Financials - Cash Management
ERP-FIN-94 | The Financial solution shall allow for integration to enable automated data exchange between the financial ERP and banks, supporting bank statement reconciliation, cash flow management, and financial reporting. | Financials | Phase 1
ERP-FIN-95 | The Financial solution shall automatically or manually fetch bank statements from multiple banking institutions. | Financials | Phase 1
ERP-FIN-96 | The Financial solution should support industry-standard formats (e.g., MT940, BAI2, CAMT.053). | Financials | Phase 1
ERP-FIN-97 | The Financial solution must match bank transactions with ledger entries automatically. | Financials | Phase 1
ERP-FIN-98 | The Financial solution should allow users to manually reconcile unmatched transactions. | Financials | Phase 1
Financials - HR Integration
ERP-FIN-99 | The Financial solution shall seamlessly retrieve payroll reporting from the payroll processing system on a weekly basis. The proposer should include all standard connectors to Human Resources Management Systems in their initial proposal. | Financials | Phase 1
ERP-FIN-100 | The Financial solution shall ensure correct mapping of earnings, deductions and tax information to general ledger. | Financials | Phase 1
ERP-FIN-101 | The Financial solution shall post journal entries for approval and release from payroll information received from payroll processing system. | Financials | Phase 1
Financial - PMO and S2C Integration
ERP-FIN-102 | All system-to-system integrations are planned for phase 3. The proposer shall provide Interface Control Document (ICD) or Application Program Interface (API) with its proposal and describe how it will interface with each of the items below. The Proposer shall describe data available and how these integrations fit into the workflows. Allow for future integration into a commercially available PMO system that will include but not limited to: 1. Initiate Project Data (ID, Name, PM, Budget) from PMO system to Finance 2. Assigning CapEx Code to Projects from Finance to PMO system 3. Project spend tracking (Personnel and Non-Personnel) from Finance to PMO system 4. CapEx hours from Finance to PMO system (derived from ADP/Payroll processor) 5. Allow for notifications from Finance to PMO system for Budget warnings, invoice payment status update) Allow for future integration to commercially available S2C system that will include but not limited to: 1. Pull Budget information from Finance Module to S2C 2. Pull Account Number information, Asset Classification (if applicable) and Capex Project ID from Finance Module to S2C 3. Invoice and Payment status from Finance Module to S2C 4. Provide Purchase Orders (POs): Detailed information regarding purchase orders, including PO number, supplier details, and status from S2C to Finance Module 2. Provide Supplier/vendor Details: Payment terms, W9/8 info, contact information from S2C to Finance Module 3. Provide Invoices: Invoice data including invoice number, amount, and payment status from S2C to Finance Module | Financials | Phase 3
Financial - Inventory/Asset/Storeroom Management
ERP-FIN-103 | The Financial solution shall provide recommendations to change the reorder point or min/max based on lead times, usage and predicted usage and lead time that is adjusted for the season. The frequency of the notifications shall be configurable by the Company on a monthly basis. | Financials | Phase 1
ERP-FIN-104 | The Financial solution shall allow for the definition of locations/departments in order to transfer merchandise to one another. | Financials | Phase 1
ERP-FIN-105 | The Financial solution shall incorporate rounding rules into replenishment calculations based on client-side configuration rules. | Financials | Phase 1
ERP-FIN-106 | The Financial solution shall set a start and end date for a replenishment strategy Ability to report on the following: - Out-of-Stock items - Over-stock items - Low-Stock items - In-stock items across all locations | Financials | Phase 1
ERP-FIN-107 | The Financial solution shall track inventory quantities down to the style/color/size (SKU) level at all locations and provide a centralized view of what inventory stock is available at each location. | Financials | Phase 1
ERP-FIN-108 | The Financial solution shall view inventory of an item across all locations in a centralized view. | Financials | Phase 1
ERP-FIN-109 | The Financial solution shall manage price and cost between purchasing departments. | Financials | Phase 1
ERP-FIN-110 | The Financial solution shall provide near real time inventory visibility that updates a minimum of at least every 1 minute and the screens to view this formation shall have automatic refreshes of data without reloading the application. The proposer shall describe inventory management and real time updating in their initial proposal | Financials | Phase 1
ERP-FIN-111 | The Financial solution shall post inventory counts to General Ledger on a daily basis. | Financials | Phase 1
ERP-FIN-112 | The Financial solution shall allow us the ability to perform a physical inventory count either by demand or a pre-determined schedule. | Financials | Phase 1
ERP-FIN-113 | The Financial solution shall maintain and track the age of inventory movement. | Financials | Phase 1
ERP-FIN-114 | The Financial solution shall require review and approval by a pre-determined approver for physical inventory count reconciliation results prior to adjustments being posted. | Financials | Phase 1
ERP-FIN-115 | The Financial solution shall transfer merchandise and track transfers between locations. | Financials | Phase 1
ERP-FIN-116 | The Financial solution shall track shipment confirmation, quantity adjustments and receipt confirmation of transfers. | Financials | Phase 1
ERP-FIN-117 | The Financial solution shall provide reason codes for transfers or a note field that contains client-side configuration options for reason code. The proposer shall describe how to create and maintain this information through client-side configuration. | Financials | Phase 1
ERP-FIN-118 | The Financial solution shall be able to integrate inventory information from our current inventory system to the new including but not limited to inventory numbers, descriptions, min/max, UOM, vendor information such as part number/current cost | Financials | Phase 1
ERP-FIN-119 | The Financial solution shall have a catalog function with the following features: - pictures - detailed descriptions, part numbers, manufacturer name - inventory level - Mobile friendly | Financials | Phase 1
ERP-FIN-120 | The Financial solution shall track expiration dates for perishable items and send a report on out-of-date items. | Financials | Phase 1
Phase 2 - PMO Solution
Roles Based Access Control Requirements
PMO-RBAC-1 | The Solution shall create and assign distinct user roles through Active Directory Groups or Entra groups, including but not limited to Department Director, Department Manager, Project Manager, Executive Committee (ExCo) Member, ExCo Sponsor, PMO Assistant, Project Stakeholder, Resource Manager, Risk Owner, Project team member, and Issue Owner. The proposer shall describe their authentication and authorization processes in their initial proposal | PMO | Phase 2
PMO-RBAC-2 | The Solution shall define, and document specific permissions associated with each role, detailing access rights to reports, features, functions, and data. | PMO | Phase 2
PMO-RBAC-3 | The Solution shall ensure that each role has access only to the information necessary for their duties, adhering to the principle of least privilege (PoLP). | PMO | Phase 2
PMO-RBAC-4 | The Solution shall enforce access control by preventing users from accessing data and functionalities not permitted by their assigned role. | PMO | Phase 2
PMO-RBAC-5 | The Solution shall display appropriate error messages when users attempt to access restricted areas or functionalities. | PMO | Phase 2
PMO-RBAC-6 | The Solution shall facilitate periodic reviews of user roles and permissions to ensure they remain aligned with ITR needs and policies | PMO | Phase 2
PMO-RBAC-7 | The Solution shall generate reports on user role assignments and access levels for auditing purposes. | PMO | Phase 2
PMO-RBAC-8 | The Solution shall send notifications to users when their role assignments change, including details of new permissions and responsibilities. | PMO | Phase 2
PMO-RBAC-9 | The Solution shall allow users to request changes to their role assignments, which must be reviewed and approved by the PMO Director or designated authority. | PMO | Phase 2
PMO-RBAC-10 | The Solution shall provide documentation outlining role definitions, permissions, and procedures for requesting role changes. | PMO | Phase 2
PMO-RBAC-11 | The Solution provider shall include training resources to ensure users understand their roles and responsibilities within the Solution | PMO | Phase 2
PMO-RBAC-12 | The Solution shall comply with all relevant security standards and ITR & IT policies regarding access control and data protection. | PMO | Phase 2
PMO-RBAC-13 | The Solution shall provide an audit log of all role creation and modification actions for accountability and compliance. | PMO | Phase 2
PMO-RBAC-14 | The Solution shall grant PMO Director role to: 1. Create new user roles with specified permissions and access levels. 2. Update the names of existing roles to reflect changes in ITR structure or responsibilities. 3. Modify the privileges of existing roles, including granting or restricting access to specific features and data within the PMO Solution. 4. Review and approve role changes to ensure compliance with ITR policies. 5. Assign multiple roles to specific user if needed (Example: ExCo Member can be ExCo Sponsor for specific projects) | PMO | Phase 2
PMO-RBAC-15 | The Solution shall grant PMO Director role the capability to assign the ExCo Sponsor role to appropriate ExCo Members for specific projects. | PMO | Phase 2
PMO-RBAC-16 | The Solution shall grant PMO Director role full control over all aspects of the PMO Solution, including the ability to manage application group roles, permissions, and access levels for all group assignments. | PMO | Phase 2
PMO-RBAC-17 | The Solution shall grant PMO Director the capability to configure and customize dashboards, reports, and project settings. | PMO | Phase 2
PMO-RBAC-18 | The Solution shall grant the Project Manager role the capability to view, update and edit all information related to the projects they are assigned to, including requesting resources, generating reports and dashboards, updating status, logging risks, issues, and changes to project plans. | PMO | Phase 2
PMO-RBAC-19 | The Solution shall grant the Project Manager role the capability to request role assignments for team members, which must be approved by the PMO Director. | PMO | Phase 2
PMO-RBAC-20 | The Solution shall grant ExCo Member role the capability to view the dashboards, and any information related to all projects within the PMO. | PMO | Phase 2
PMO-RBAC-21 | The Solution shall grant ExCo Member role and Department Director role read-only access to view monthly and weekly dashboards, project specific reports, performance metrics, and any information related to all projects within the PMO without the ability to modify any information. | PMO | Phase 2
PMO-RBAC-22 | The Solution shall grant ExCo Sponsor role and Department Director role the ability to review and approve the following items scope, schedule baseline, budgets, and key deliverables as well as providing feedback and direction on projects plans and objectives for the projects they are sponsoring. | PMO | Phase 2
PMO-RBAC-23 | The Solution shall grant PMO Assistant role the capability to assist the PMO Director with various duties, including: 1. Managing user accounts, which include creating, editing, and deactivating user accounts as needed. 2. Generating reports on project status, performance metrics, and resource allocation. 3. Viewing all project information, including risks, issues, and timelines across all projects within the PMO. 4. Updating project statuses as directed by the PMO Director, ensuring that all changes are accurately reflected in the system. 5. Assisting with administrative tasks, such as scheduling meetings and organizing project documentation. | PMO | Phase 2
PMO-RBAC-24 | The Solution shall grant Project Stakeholder role read-only access to view information and sign requested approvals related to the specific projects in which they are stakeholders. | PMO | Phase 2
PMO-RBAC-25 | The Solution shall grant Resource Manager role read-only access to view information related to their resources assigned to projects across PMO. | PMO | Phase 2
PMO-RBAC-26 | The Solution shall grant Risk Owner role write access to edit and update only the risks assigned to them, which includes changing the status, updating response plans, and logging comments. | PMO | Phase 2
PMO-RBAC-27 | The Solution shall grant Issue Owner role write access to edit and update only the issues assigned to them, including changing status, adding comments, and updating resolution plans. | PMO | Phase 2
Integration
PMO-IN-1 | The solution shall allow integration with other applications by providing the capability to securely export and import data using flat-file formats (e.g., CSV, JSON) and PDF and API-based integration methods. It's desired that any web services use REST based services and system to system authentication controls. | PMO | Phase 3 - Low Priority
PMO-IN-2 | The solution shall integrate with the Accounting and Finance module of Microsoft Dynamics GP (MS GP) or any other ERP system as well as ADP (for payroll processing) to extract the following data for each project within the PMO: 1. Actual Costs Incurred: - Labor Costs: Costs associated with labor (salaried and hourly) without revealing the specific salaries or hourly rates for resources working on the project. - Non-Labor Costs: All other project-related expenses, including materials, services, and overhead costs. 2. Employee Information: - Name: The name of the employee. - Role: The role of the employee for stakeholder identification, approval workflow, and resource assignment purposes. The proposer shall provide a list of all out of the box ERP integrations provided by their product in their initial proposal. | PMO | Phase 3
PMO-IN-3 | The solution shall integrate with the Procurement module of Microsoft Dynamics GP (MS GP) or any other ERP system to extract data related to the following procurement elements: | PMO | Phase 3
1. Purchase Requisition (PR)
2.Purchase Orders (POs): Detailed information regarding purchase orders, including PO number, supplier details, and status.
3. Request for Information (RFI): Data related to RFIs, including request details and responses.
4. Request for Proposal (RFP): Information on RFPs, including proposals received and their status.
5. Invitation for Bid (IFB): Details regarding IFBs, including invitations sent and bid status.
6. Vendor Cost Assessment (VCA)
7. Contacts: Supplier/vendor contact information and details.
8. Invoices: Invoice data including invoice number, amount, and payment status.
9. Vendor performance tracking and scoring.
PMO-IN-4 | The solution shall provide a built-in scheduling capability or allow integration with a commercial project scheduling tool (e.g., Microsoft Project, Primavera, Smartsheet) to allow the development or consumption of the following schedule data: | PMO | Phase 3
1. Activities: Detailed information about project activities (start date, duration, end date, predecessors, successors) including work breakdown structure and critical path activities.
2. Resources: Data related to project resources.
3. Project Status: Status and overall progress of the project.
4. Costs: Financial data including project costs and budget information.
5. Gantt Chart View: Visualization of the project schedule through Gantt charts.
6. Earned Value Management (EVM) Metrics: Metrics related to project performance and progress.
7. Milestone List: List of project milestones and their status.
8. Resource Allocation: Information on how resources are allocated across activities and projects.
The Proposer shall describe native connectors available for commercial project schedulers.
PMO-IN-5 | The solution shall provide the capability to integrate with a timesheet application or a timesheet module within an ERP system, enabling stakeholders and project teams to log Capital Expenditure (CapEx) hours against specific projects to which they are assigned. | PMO | Phase 3
PMO-IN-6 | The solution shall enable the import and export of project documentation (e.g., change orders, invoices, reports) to and from document management systems (e.g., SharePoint, Google Drive) following ITR Folder Structure and File Naming Convention Guideline. | PMO | Phase 3
PMO-IN-7 | The Solution shall support integration with Entra ID to retrieve the names, titles, and departments of ITR employees for stakeholder identification, project communications, and Resource assignment purposes. This integration shall be one-way, from AD/Entra ID to the Solution. It must ensure that data is protected and comply with all relevant IT policies pertaining to data integrity and security. | PMO | Phase 3 - Low Priority
PMO-IN-8 | The Solution shall provide a standard data dictionary including data description, title, data type and if required in any API. The documentation shall describe flow control and encryption (at rest or in transit) of all data available to external interfaces. | PMO | Phase 3
PMO-IN-9 | The Solution shall provide for an ETL (extract, transform, load) Connection for project data to extract data from the Solution from a third-party Enterprise Data Warehouse solution. | PMO | Phase 3
PMO-IN-10 | The Solution shall provide the capability to integrate with Microsoft Outlook Calendar to enable two key capabilities: Stakeholder Scheduling: Project Managers shall be able to schedule project-related meetings (e.g., kick-off, reviews) directly from the stakeholder register within the Solution. The system shall generate Outlook calendar invites that include meeting details (title, agenda, time, location or virtual link, attachments) and send them to selected stakeholders. The activity shall be logged for audit purposes. Resource Availability: The integration shall provide real-time visibility into resource availability by syncing with individual calendars in Microsoft Outlook. Resource Managers shall use this data to efficiently allocate or reallocate resources across projects based on actual availability. This integration shall support bi-directional synchronization and respect user access permissions and organizational calendar policies. | PMO | Phase 2
PMO-IN-11 | The Solution shall support integration with SurveyMonkey (or any other survey application) to retrieve survey data and convert it into actionable insights using predefined metrics (e.g. Stakeholder Satisfaction Index -SSI) and analytics tools. | PMO | Phase 3
General Requirements
PMO-GR-1 | The proposer must provide options for how notifications will be delivered/handled as referenced across requirements. | PMO | Phase 2
PMO-GR-2 | The proposer must specify how workflow will be developed, and configured for various purposes, as referenced across the requirements. Examples of workflows: Review and Approval of requirements and scope, change request/order, budget-related adjustments, invoice payments, lessons learned, etc. | PMO | Phase 2
PMO-GR-3 | The Solution shall maintain a comprehensive audit trail of all user and system activities, including approvals, comments, feedback, modifications to data, and configuration changes, to ensure accountability, traceability, and transparency. | PMO | Phase 2
PMO-GR-4 | The Solution shall allow PMO Director to create, store, update, and manage a centralized PMO Artifact Library that includes processes, templates (e.g., checklists, registers, logs, matrices, plans, and tables), and guidelines to support PMO operations across all phases of the Project Life Cycle (PLC). The library shall support: | PMO | Phase 2
1. Creating and configuring in-built templates
2. Proper naming, indexing, and categorization of artifacts by project phase
3. Role-based access, ensuring authorized Project Managers can access and utilize the artifacts as needed
4. Search and filter capabilities based on artifact type, project phase, and category
The Solution shall notify all authorized Project Managers whenever a new artifact is created, an existing artifact is updated, or an artifact is archived in the PMO Artifact Library.
PMO-GR-5 | The Solution shall allow Project Manager to access and navigate the PMO Artifact Library, search for specific artifacts, and apply selected artifacts to support their project activities. | PMO | Phase 2
PMO-GR-6 | The Solution shall provide mobile access for users to manage projects and receive notifications. | PMO | Phase 2
Project Initiation
PMO-PI-1 | The Solution shall allow the Project Manager to develop a project charter using pre-built templates, which can be customized to fit the specific needs of a project. The project charter template should include, as a minimum, the components outlined in the project charter template, with the ability to attach or link to documents. Additionally, the Solution shall support the review and approval process by specified stakeholders. | PMO | Phase 2 - Medium Priority
PMO-PI-2 | The Solution shall allow the ExCo Sponsor and/or Departmental Director/Manager and any other specified stakeholders to review and/or approve the project charter. | PMO | Phase 2
PMO-PI-3 | The Solution shall notify Project Manager when their project charter has been reviewed and/or approved. | PMO | Phase 2
PMO-PI-4 | Upon the project charter approval, the Solution shall allow Project Manager to submit a Project Initiation Request (PIR) to initiate a new project within the PMO via a built-in form or outside of application document. The request must include the following details: (Which can be automatically populated from the project charter as per PMO-PI-1)
1. Project Name,
2. Project Description,
3. Project Size (Medium, Large),
4. Department (F&P, HUB, INF, IT, Legal, OPS, Toll Ops),
5. Project Manager,
6. Executive Sponsor (ExCo Sponsor),
7. Project Owner/Point of Contact (POC) – if applicable,
8. Approved Budget,
9. Date Budget approved,
10. Budget Approved Authority
o Approved capex budget
o Approved OpEx budget
o ExCo delegated authority
o CEO delegated authority
11. Planned Start Date,
12. Planned End Date,
13. Planned Duration (months),
14. Attachments or links (at least: Business Case, Project Charter)
15. Key Stakeholders. For each key stakeholder identified, the following details must be included:
o Name
o Company Name
o Title
o Role in the Project
o Email Address
o Phone Number
o Internal/External
PMO-PI-5 | The Solution shall notify PMO Director within 2-5 minutes of the Project Initiation Request (PIR) submission by email and within the system. | PMO | Phase 2
| The Solution shall maintain a log of all Project Initiation Requests (PIRs). | PMO | Phase 2
PMO-PI-6
PMO-PI-7 | The Solution shall provide PMO Director with the capability to acknowledge receipt of the Project Initiation Request (PIR) and to add a customized message relevant to the request. | PMO | Phase 2
PMO-PI-8 | The Solution shall provide the PMO Director with the capability to update the status of Project Initiation Request (PIR) as well as adding any additional information. The available status options must include Received, In Process, Under Revision, Approved, Pending, and Rejected. Under Revision status indicates that the requesting project manager has been asked to modify the request. | PMO | Phase 2
PMO-PI-9 | The Solution shall allow the requesting project manager to update the request if the status is set to “Under Revision by the PMO Director. | PMO | Phase 2
PMO-PI-10 | The Solution shall allow the Project Manager to check the status of Project Initiation Requests (PIRs) that they have submitted. | PMO | Phase 2
PMO-PI-11 | The Solution shall provide the PMO Director with the capability to send a request to the Finance Department to open a Project Accounting Code (PAC) for projects that have been approved for initiation. The request must include the following details: | PMO | Phase 2
1. Project Name
2. Project Manager
3. Department (F&P, HUB, INF, IT, Legal, OPS, Toll Ops),
4. Approved Budget
5. Project Description
6. Executive Sponsor (ExCo Sponsor)
7. Start Date
8. Expected End Date
The proposer must provide options for how this request will be sent between the two applications.
PMO-PI-12 | The Solution shall allow the Finance Assistant Manager or any designated department employee to add the assigned Project Accounting Code (PAC) to the project initiation request if this task is not automated through system integration. | PMO | Phase 2
PMO-PI-13 | The Solution shall notify the PMO Director when their request to open a Project Accounting Code (PAC) is complete. The notification must include PAC created. | PMO | Phase 2
The proposer must provide options for how this notification will be delivered.
PMO-PI-14 | Upon the Project Accounting Code (PAC)'s creation, the Solution shall let PMO Director update the project initiation request (PIR) with the PAC value and update the request status to "Approved". | PMO | Phase 2
PMO-PI-15 | Upon the Project Initiation Request (PIR) status changing to “Approved,” the Solution shall notify project manager that their request has been approved. | PMO | Phase 2
PMO-PI-16 | Upon the Project Initiation Request (PIR) status changing to “Approved”, the Solution shall add a new entry to the project database with all the information from the PIR in addition to the following information: | PMO | Phase 2
1. PMO Serial # (Incremental Counter)
2. Project ID (Automatically Generated) **
3. Status set to "Initiated"
4. Phase in Project Life Cycle (PCL) set to "Initiating"
**The Project ID must be formatted as: PMO-[Department Abbreviation]-[Two-Digit Year]-[Three-Digit Serial Number]. Example : PMO-IT-24-001, PMO- INF-24-002
Here is the list of ITR Department Abbreviations:
BM = Building Maintenance
EHS = Environmental, Health, and Safety
FP = Finance and Procurement
HUB = HR, Corporate Strategy, ESG, Communications, and
Customer Service
INF = Infrastructure
IT = Information Technology
RW = Road Way
TM = Traffic Management
TO = Toll Operations
The proposer shall describe their process for naming projects and configurations and their client-side configuration abilities in their initial proposal.
PMO-PI-17 | Upon the addition of a project entry — as per PMO-PI-16 — the Solution shall automatically create a Stakeholder Register, populate it with the stakeholders listed in the project initiation request, and send a notification to the project manager confirming its creation. | PMO | Phase 2
PMO-PI-18 | Upon receiving notification of the creation of the Stakeholder Register, the solution shall allow the Project Manager to add additional stakeholders to the register, with stakeholder details added either manually or via file import. For each stakeholder identified, the following details must be included: | PMO | Phase 2
1. Name
2. Company Name
3. Title
4. Role in the Project
5. Email Address
6. Phone Number
7. Internal/External
PMO-PI-19 | Upon approval of the Project Initiation Request (PIR), the Solution shall automatically populate the Risk Register, Assumption and Constraint Log, and Dependency Log with any risks, assumptions and constraints, and dependencies, respectively, that are captured in the project charter. | PMO | Phase 2
PMO-PI-20 | The Solution shall allow the Project Manager to send a notification to stakeholders— as captured in the stakeholder register— as well as to the ITRCC ExCo, ITRCC PMO, and Procurement distribution lists by informing them of the official initiation of the project and outlining the next steps. | PMO | Phase 2
The proposer must provide options for how this notification will be delivered.
PMO-PI-21 | The Solution shall either automatically assig or allow the PMO Director to assign a project document repository for the initiated project, provide Project Manager with owner access to the repository, and notify Project Manager of the repository assignment. | PMO | Phase 2
PMO-PI-22 | Upon receipt of the notification for repository assignment, the solution shall allow the Project Manager to add stakeholders to the project repository and assign different levels of access to them. | PMO | Phase 2
Planning, Executing, Monitoring, & Controlling (PEMC)
PEMC – Delivery Approach & Planning
PMO-PEMC-1 | The Solution shall support the configuration and management of projects using either Waterfall, Agile, or hybrid methodologies based primarily on the PMI PMBOK® Guide and Agile Alliance principles, unless otherwise explicitly specified by the requirement. | PMO | Phase 2
PMO-PEMC-2 | The Solution shall support the application of multiple project delivery approaches based on project type. The Solution shall support infrastructure delivery methods (such as Design-Bid-Build, Design-Build, and CM/GC) as well as IT/technology SDLC (requirements analysis, design, implementation, testing, deployment, and maintenance). | PMO | Phase 2
PMO-PEMC-3 | The Solution shall allow Project Manager to select and configure the project delivery approach and methodology (Waterfall, Agile, Hybrid) at the start of the planning phase. | PMO | Phase 2
PMO-PEMC-4 | The Solution shall allow the Project Manager to create, update, and maintain version control of the Project Management Plan (PMP), either by using a built-in template or by integrating subsidiary management plans (scope, schedule, cost, quality, resource, risk, communication, procurement, stakeholder, EHS, Sustainability, and Document Management). The Solution shall also allow Project Manager to route the completed or updated PMP for review and approval. | PMO | Phase 2
PMO-PEMC-5 | The Solution shall support the creation and comparison of multiple project baselines (scope, cost, schedule). | PMO | Phase 2
PMO-PEMC-6 | The Solution shall allow PMO Director to assign relevant KPIs to projects– based on the delivery approach and methodology used- during the planning phase, along with corresponding targets. | PMO | Phase 2
PMO-PEMC-7 | The Solution shall allow PMO Director to assign relevant KPIs to projects– based on the delivery approach and methodology used- during the planning phase, along with corresponding targets. | PMO | Phase 2
PEMC – Scope & Scheduling
PMO-PEMC-8 | The Solution shall allow PMO Director to assign relevant KPIs to projects– based on the delivery approach and methodology used- during the planning phase, along with corresponding targets. | PMO | Phase 2
PMO-PEMC-9 | The Solution shall allow Project Manager to create and update Project Scope Statement by using a built-in template and route it for review and approval. | PMO | Phase 2
PMO-PEMC-10 | The Solution shall support the creation, visualization, and baselining of Work Breakdown Structure (WBS). | PMO | Phase 2
PMO-PEMC-11 | The Solution shall allow sprint creation, resource allocation, and task tracking within each sprint. | PMO | Phase 2
PMO-PEMC-12 | The Solution shall support Gantt charts and other visual tools for effective project planning and scheduling. | PMO | Phase 2
PMO-PEMC-13 | The Solution shall enable Project Manager to create and update project plans, including timelines, milestones, and deliverables at all the phases of the project life cycle. | PMO | Phase 2
PMO-PEMC-14 | The solution shall allow Project Manager to upload third-party schedules either as standalone schedules or merge them with other existing schedules to create an integrated project schedule. The solution must ensure that dependencies, durations, and resource allocations from the third-party schedule are properly preserved during the upload and merge process. | PMO | Phase 2
PEMC - Cost & Budgeting
PMO-PEMC-14 | The Solution shall allow Project Manager to develop cost estimates at the planning phase including line items for various cost categories (e.g., labor, materials, contractor/vendor, overhead, etc.), aggregate those budget line items to develop a project cost estimate, and route it for approval to ExCo Sponsor and Departmental Director/Manager. | PMO | Phase 2
PMO-PEMC-15 | The Solution shall allow ExCo Sponsor to allocate contingency funds for unforeseen expenses (risks, change orders, etc.) and manage their utilization. | PMO | Phase 3
PMO-PEMC-16 | The Solution shall notify Project Manager when a contingency has been allocated to their projects. | PMO | Phase 3
PMO-PEMC-17 | The solution shall l track the difference between the approved budget and Budget at Completion (BAC) of the project cost baseline in a budget category called "Remaining Approved Budget." | PMO | Phase 3
PMO-PEMC-18 | The Solution shall allow Project Manager to establish a project cost baseline (Budget at Completion or BAC) once the project cost estimate is finalized and contingency funds have been allocated. The Solution shall also support maintaining up to five cost baselines for comparison and historical tracking of project performance. The Project Cost Baseline (BAC) is defined as the sum of the Project Cost Estimate and the allocated Contingency. | PMO | Phase 3
PMO-PEMC-19 | The Solution shall provide tools for tracking actual expenditures against approved budgets and approved cost baseline in real-time. | PMO | Phase 2
PMO-PEMC-20 | The Solution shall enable ExCo Sponsor to reallocate budgeted funds between categories or projects, subject to appropriate approvals. This shall allow for budget allocation at a program/bucket level and the projects within a program/bucket. | PMO | Phase 3
PMO-PEMC-21 | The Solution shall notify Project Managers whenever an expense is logged into their project. | PMO | Phase 3
PMO-PEMC-22 | The Solution shall provide tools for conducting cost-benefit analyses to evaluate the financial viability of projects and initiatives. | PMO | Phase 3
PMO-PEMC-23 | The Solution shall notify ExCo members and relevant stakeholders of significant budget changes, variances, or approvals required. | PMO | Phase 3
PMO-PEMC-24 | The Solution shall maintain an audit trail of all budget-related changes, approvals, and comments for accountability and transparency. | PMO | Phase 3
PMO-PEMC-25 | The Solution shall support an approval workflow for budget revisions and additional funding requests to ensure accountability. | PMO | Phase 3
PMO-PEMC-26 | The Solution shall provide tools for tracking actual expenditures against approved budgets in near real-time not to exceed 5 minutes. | PMO | Phase 3
PMO-PEMC-27 | The Solution shall allow Project Manager to manage and control project budgets, including tracking expenses and performing variance analysis by comparing planned budgets with actual costs, and automatically highlighting discrepancies. | PMO | Phase 3
PMO-PEMC-28 | The Solution shall enable Project Manager to forecast future costs based on current spending trends and project progress. | PMO | Phase 3
PMO-PEMC-29 | The Solution shall allow Project Manager to update and track costs associated with resource allocations, including labor hours and utilization. | PMO | Phase 3
PMO-PEMC-30 | The Solution shall create and maintain a Master Project Cost Register that captures and consolidates all project-related financial transactions across all active and closed projects in the PMO. The Master Project Cost Register shall include, at a minimum, the following fields for each expense entry with configurable default values: | PMO | Phase 2
1. Project ID
2. Project Name
3. Project Accounting Code (PAC)
4. Project Manager
5. WBS/Cost Code/Budget Line Item
6. Expense Category (e.g., Internal CapEx Cost, External Labor, Materials, Equipment, Consulting Services, Construction Services, Software License and Support, Permit Fees, etc.)
7. Description of Expense
8. Vendor/Supplier Name
9. PO/Contract ID/MSA (if applicable)
10. Invoice Number
11. Invoice Received Date
12. Invoice Due Date
13. Invoice Amount
14. Payment Type (Advance Payment, Progress Payment, Final Payment, One-time Payment)
15. Status (e.g., Pending Approval, Approved, Paid, Disputed, Cancelled)
16. Payment Date
17. Method of Payment (Bank Transfer, Credit/Debit Card, Check)
18. Paid By
19. Retainage
20. Notes/Comments
This register shall allow filtering and searching by Project Name, Vendor, Payment status, Expense Category, and Invoices and their status.
PMO-PEMC-31 | The Solution shall allow Project Manager, PMO Assistant, and authorized personnel from the Procurement and Finance Departments to create, edit, and update project expense entries in the Master Project Cost Register. | PMO | Phase 2
PMO-PEMC-32 | The Solution shall allow PMO Director and authorized personnel from the Finance department to import monthly CapEx hours and their associated costs for both salaried and hourly employees, covering all projects—including PMO and non-PMO projects—into a dedicated CapEx Hours Database within the Solution. | PMO | Phase 2
The import file must include the following mandatory fields:
1. Project Name
2. Project Accounting Code (PAC)
3. Reporting Month
4. Total Hours for Salaried Employees
5. Total Hours for Hourly Employees
6. Total Combined Hours
7. Total Cost of Hours (excluding hourly rates or individual salary details)
PMO-PEMC-33 | The Solution shall notify Project Managers upon the successful import of CapEx hours into the CapEx Hours Database, provided their projects are included in the import batch. | PMO | Phase 2
PMO-PEMC-34 | The Solution shall allow PMO Director and authorized personnel from the Finance department to make updates or corrections to previously imported CapEx Hours and associated cost records. The system shall retain version history for all changes, including the original values, updated values, date/time of modification, and the identity of the user making the change. | PMO | Phase 2
PMO-PEMC-35 | The Solution shall allow Project Manager to view the number of CapEx hours reported under their projects with the option to choose the month and year. | PMO | Phase 2
PMO-PEMC-36 | The Solution shall support Earned Value Management (EVM) by tracking Planned Value (PV), Earned Value (EV), and Actual Cost (AC), and by automatically calculating the following key performance indicators: Cost Performance Index (CPI), Schedule Performance Index (SPI), Estimate at Completion (EAC), and Variance at Completion (VAC). | PMO | Phase 3
PEMC – Communications & Stakeholders
PMO-PEMC-37 | The Solution shall include built-in messaging via SMS or email or notifications within the applications to facilitate communication among project stakeholders. | PMO | Phase 2
PMO-PEMC-38 | The Solution shall provide tools for scheduling and managing project meetings, including agenda creation and minute tracking or integrating with Microsoft collaboration and business productivity tools including MS Outlook, MS Teams and MS SharePoint. | PMO | Phase 2
PMO-PEMC-39 | The Solution shall enable the Project Manager to assign action items during meetings and monitor their completion. | PMO | Phase 2
PMO-PEMC-40 | The Solution shall allow Project Manager to classify the current engagement level of each stakeholder using a built-in Stakeholder Engagement Assessment Matrix, define the desired engagement level, and monitor engagement throughout project planning and execution by comparing the current engagement level against the desired engagement level. The Solution shall support periodic updates and reporting on engagement shifts over time. | PMO | Phase 2
PMO-PEMC-41 | The Solution shall allow Project stakeholders to comment on project updates, documents, and issues directly within the Solution or through using configurable surveys and feedback forms. | PMO | Phase 2
PMO-PEMC-42 | The Solution shall allow Project Team Member to collaborate and share documents with project manager and rest of the project team. | PMO | Phase 2
PEMC - Document Management
PMO-PEMC-43 | The solution shall provide functionality for the PMO Director to upload documents either to the overall PMO repository or to a repository specific to a particular project group of projects. | PMO | Phase 2
PMO-PEMC-44 | The Solution shall provide a centralized repository for project documents, including contracts, proposals, and reports, accessible to authorized users. | PMO | Phase 2
PMO-PEMC-45 | The Solution shall support version control and document collaboration features for team members. | PMO | Phase 2
PMO-PEMC-46 | The solution shall provide functionality for the project managers, Department Director, and ExCo Sponsor to upload documents either to the overall PMO repository or to a repository specific to one of their projects. | PMO | Phase 2
PMO-PEMC-47 | The Solution shall enable Project Stakeholders to upload relevant project documents to the designated project repository. The Solution shall allow one or more documents to be uploaded. | PMO | Phase 2
PEMC - Environmental, Health and Safety (EHS)
PMO-PEMC-48 | The Solution shall enable the definition, tracking, and reporting of EHS Key Performance Indicators (KPIs) to evaluate project EHS performance, including but not limited to incident rates, compliance rates, and training completion rates. | PMO | Phase 2
PMO-PEMC-49 | The Solution shall allow for the tracking of compliance with industry-specific EHS regulations and standards applicable to the projects, including automated compliance checklists and reporting mechanisms for non-compliance. | PMO | Phase 2
PMO-PEMC-50 | The Solution shall provide features for scheduling and documenting EHS training sessions for stakeholders, including attendance records and training content, to ensure compliance with safety standards and procedures. | PMO | Phase 2
PMO-PEMC-51 | The Solution shall facilitate the scheduling and conducting of EHS audits and inspections to assess compliance with EHS standards and regulations, including both internal and external audits, with automated reminders for upcoming audits. | PMO | Phase 2
PMO-PEMC-52 | The Solution shall facilitate the scheduling and conducting of EHS audits to assess compliance with established standards and identify areas for improvement, including tracking the status of audit findings and recommendations. | PMO | Phase 2
PMO-PEMC-53 | The Solution shall allow Project stakeholders to log corrective actions resulting from audits or incident investigations, including details on responsible parties, deadlines for completion, and the status of implementation, with reminders for overdue actions. | PMO | Phase 2
PMO-PEMC-54 | The Solution shall enable Project stakeholders to report EHS incidents, accidents, or near misses in real-time, capturing essential details such as date, time, location, description of the incident, individuals involved, and any immediate corrective actions taken. | PMO | Phase 2
PEMC - ITR Project Management Framework (IPMF) Compliance
PMO-PEMC-55 | The Solution shall include a feedback mechanism for Project stakeholders to provide input on the ITR Project Management Framework and suggest improvements. | PMO | Phase 2
PMO-PEMC-56 | The Solution shall notify PMO Director when a non-compliance instance with the ITR Project Management Framework is logged. | PMO | Phase 2
PMO-PEMC-57 | The Solution shall allow Project Manager to document instances of non-compliance with the ITR Project Management Framework and specify corrective actions. | PMO | Phase 2
PMO-PEMC-58 | The solution shall allow all users of the product to view and download template and workflow documentation | PMO | Phase 2
PEMC - Data Analytics and Search Functionality
PMO-PEMC-59 | The Solution shall offer search and filter functionalities to allow ITR users to easily access specific lessons learned based on keywords, categories, or project names. | PMO | Phase 2
PMO-PEMC-60 | The Solution shall provide a workflow for submitting lessons learned for review and approval by the PMO Director or designated reviewers. | PMO | Phase 2
PMO-PEMC-61 | The Solution shall offer search and filter functionalities to allow users to easily access specific lessons learned based on keywords, categories, or project names. | PMO | Phase 2
PMO-PEMC-62 | The Solution shall notify relevant stakeholders when new lessons learned are documented or when updates are made to existing lessons. | PMO | Phase 2
PMO-PEMC-63 | The Solution shall enable Project Managers and stakeholders to document lessons learned during and after each project phase or milestone. | PMO | Phase 2
PMO-PEMC-64 | The Solution shall provide mobile access for users to manage projects and receive notifications. | PMO | Phase 2
PEMC - Procurement
PMO-PEMC-65 | The Solution shall allow Project Manager to create and finalize a Scope of Work (SOW) using a customizable built-in template, route it for approval within the PMO Solution, and export the finalized, approved SOW in a standard format (e.g., PDF, DOCX). The exported SOW shall be suitable for manual attachment or import into Strategic Sourcing and Contract Management (S2C) as part of the procurement request (PR) as per ERP-S2C-132. | PMO | Phase 3
PMO-PEMC-66 | The Solution shall create and maintain a Procurement Progression Matrix to capture all active procurement activities across all projects managed by the PMO. Upon creation of each procurement entry, the Solution shall automatically set the default status of all workflow stages to "Not Started," except for Stage 9 (Approver) and Stage 10 (Assigned Delegate), which shall remain blank or configurable. For each procurement entry, the following data must be captured: Project ID, Project Name, Procurement Description, and the full Procurement Workflow, consisting of the following stages: | PMO | Phase 3
1. SOW Development
2. Contractor/Vendor/Supplier Identification
3. RFP/RFQ/IFB
4. Bid Evaluation & Comparison (VCA)
5. Contractor/Supplier Selection
6. Contract Development
7. Legal Contract Review & Approval
8. Contract Negotiation & Adjustments
9. Approver (configurable dropdown list)
10. Assigned Delegate (if needed)
11. Contract Approval
12. Contract Execution
13. Contract Management
14. Post Contract Review
PMO-PEMC-67 | The Solution shall allow Project Manager to view and check the status of procurement activities across their assigned projects. | PMO | Phase 3
PMO-PEMC-68 | The Solution shall allow PMO Director to view and check the status of procurement activities across all projects in the portfolio, with the ability to filter by project name, project manager, and procurement status. | PMO | Phase 3
PMO-PEMC-69 | The Solution shall allow the Procurement Manger or authorized Procurement personnel to, manually or through file import, enter and maintain all contract records for projects managed within the PMO. The Solution shall also allow authorized Procurement personnel to update, amend, or close contract records throughout the contract lifecycle. Each contract entry shall capture, at minimum, the following information: | PMO | Phase 3
1. Project ID
2. Project Name
3. Contract Title/Description
4. Contractor/Vendor/Supplier Name
5. Contract Number
6. Contract Type (e.g., Fixed Price, Time and Materials, Cost Reimbursable)
7. Original Contract Value
8. Current (Amended) Contract Value (if applicable)
9. Contract Start Date
10. Contract End Date
11. Status (e.g., Draft, Executed, Active, Completed, Terminated)
12. Contract Manager (Procurement Point of Contact)
13. Linked Procurement Activity (if applicable)
PEMC - Quality
PMO-PEMC-70 | The Solution shall allow the PMO Director and Project Managers to track compliance with industry standards, regulations, and organizational policies related to quality and Safety | PMO | Phase 2
PMO-PEMC-71 | The Solution shall enable PMO Director and Project Managers to define quality standards and objectives for each project at the planning stage. | PMO | Phase 2
PMO-PEMC-72 | The Solution shall provide tools for monitoring project deliverables against established quality criteria and standards. | PMO | Phase 2
PMO-PEMC-73 | The Solution shall allow Project Managers to schedule and conduct quality assurance audits throughout the project lifecycle. | PMO | Phase 2
PEMC - Resource
PMO-PEMC-74 | The Solution shall enable cross-project resource allocation and forecasting regardless of methodology. | PMO | Phase 2
PMO-PEMC-75 | The Solution shall provide a real-time dashboard that displays resource availability and current allocation across all projects, ensuring resources are neither over-allocated nor under-utilized across different projects. Changes due to schedule updates will be reflected in this dashboard, with visual indicators (e.g., color-coding) for resource allocation status. | PMO | Phase 2
PMO-PEMC-76 | The Solution shall allow for multi-resource allocation (e.g., personnel, equipment, or other entities) across multiple projects. | PMO | Phase 2
PMO-PEMC-77 | The Solution shall have the ability to forecast resource demand based on upcoming project needs (using historical data, schedules, and resource utilization trends), allowing project managers to plan for future resource requirements and address potential gaps in advance. | PMO | Phase 2
PMO-PEMC-78 | The solution shall have automated notifications & alerts when resources are approaching over- or under – allocation, ensuring proactive adjustments are made. | PMO | Phase 2
PMO-PEMC-79 | The Solution shall allow Project Manager to place a project resource requisition to their project. This functionality must include: | PMO | Phase 2
1. Resource Type: Personnel, equipment, materials, etc.
2. Resource Role (if applicable): For example, Developer, Designer, Analyst.
3. Quantity/Number of Resources: Specific number of resources needed.
4. Skills/Expertise Required: Clear description of the required skill set or expertise.
5. Start and End Dates: Duration for which the resources are required.
6. Priority: Indicate if the requisition is high, medium, or low priority
7. Justification/Reason for the Request: A field for the Project Manager to provide the business or project-related reason for the requisition.
8. Budget Estimate (if applicable): Estimated cost associated with the resource requisition.
PMO-PEMC-80 | The Solution shall notify Resource Manager upon the creation of a project resource requisition. | PMO | Phase 2
PMO-PEMC-81 | The Solution shall allow Resource Manager to approve, deny, or modify project resource requisitions, with the option to propose alternative resources or time allocations, as well as adding a customized message with the denial/modification/approval. | PMO | Phase 2
PMO-PEMC-82 | The Solution shall notify the resource upon assignment. | PMO | Phase 2
PMO-PEMC-83 | The Solution shall allow Project Team Member to view their current assignments to various projects, along with the details of each activity (Start Date, End Date, Duration, Predecessors, Successors) with the option to filter or sort their assignments by project, activity, or date. | PMO | Phase 2
PMO-PEMC-84 | The Solution shall allow Project Team Members to update their activities under each project they are assigned to. Updates shall include the following fields: Start Date, End Date, Percentage Completion, and Status (Not Started, In Progress, Completed). This update must be reflected in real-time in the resource dashboard as per PMO-PEMC-75. | PMO | Phase 2
PMO-PEMC-85 | The Solution shall allow Project Team Member with the capability to view their calendar with all the activities assigned. This capability shall also allow for synchronization with MS Outlook calendar. | PMO | Phase 2
PMO-PEMC-86 | The Solution shall notify Resource Manager with the changes in the allocation duration of their resources based on the schedule updates. | PMO | Phase 2
PMO-PEMC-87 | The Solution shall allow Resource Manager to receive on-demand resource utilization reports that highlight any changes in their resource allocations due to project schedule updates. | PMO | Phase 2
PMO-PEMC-88 | If the change in the allocation of a resource exceeds 10%, the Solution shall automatically reopen the request associated with that resource, reroute it to the Resource Manager for approval, and allow them to deny, approve or propose adjustments to the new allocation. | PMO | Phase 2
PEMC - Solution Feedback
PMO-PEMC-89 | The Solution shall include a feedback mechanism for all Project Stakeholders to provide input on the Solution and suggest improvements. | PMO | Phase 2
PMO-PEMC-90 | The feedback survey shall be customized by the PMO Director or Project manager to have global required fields and specific fields for each project. | PMO | Phase 2
PMO-PEMC-91 | Survey results shall be collected and exported in CSV, PDF by the portfolio, project type or individual project. | PMO | Phase 2
PEMC - Status Update
PMO-PEMC-92 | The Solution shall allow Procurement Manager or their authorized delegate to update the status of each procurement workflow stage in the Procurement Progression Matrix with one of the following statuses: "In Progress" or "Completed.". | PMO | Phase 2
PMO-PEMC-93 | The Solution shall allow Project Manager to document the major accomplishments for a specific week, with the option to enter the start and end dates of that week. | PMO | Phase 2
PMO-PEMC-94 | The Solution shall allow Project Manager to document the major accomplishments for a specific month, with the option to enter the month and the year. | PMO | Phase 2
PMO-PEMC-95 | The Solution shall allow Project Manager to document the major activities planned for a specific week, with the option to enter the start and end dates of that week. The definition of a week shall be configurable at the portfolio level. | PMO | Phase 2
PMO-PEMC-96 | The Solution shall allow Project Manager to document the major activities planned for a specific month with the option to enter the month and the year. | PMO | Phase 2
PMO-PEMC-97 | The Solution shall allow Project Manager to update the project phase within the project life cycle by choosing from the following options: Initiating, Planning, Executing, and Closing. | PMO | Phase 2
PMO-PEMC-98 | The Solution shall allow Project Manager to assign a percentage for progress within each phase of the project life cycle. | PMO | Phase 2
PMO-PEMC-99 | The Solution shall allow Project Manager to update the status of their project (Scope, Schedule, Cost, Resources, Safety, Risks) using the status indicators: Green, Yellow, and Red. | PMO | Phase 2
PMO-PEMC-100 | The Solution shall allow Project Manager to update the overall status of their project using the status indicators: Green, Yellow, and Red. | PMO | Phase 2
PMO-PEMC-101 | The Solution shall allow Project Team members to update the actual start date, actual finish date, activity dependencies, percentage of progress, and status (e.g., In Progress, Completed, or Done) for the activities assigned to them. | PMO | Phase 2
PEMC - Risk, Assumptions, Issues, Dependencies (RAID)
RAID - Risks
PMO-RAID-1 | The Solution shall automatically add the risks documented in the project charter upon initiation and assign the project manager as a default risk owner in the risk register. | PMO | Phase 2
PMO-RAID-2 | The Solution shall allow Project Manager to log risks identified in their projects by providing the following details: | PMO | Phase 2
1. Date the risk was identified
2. Risk description
3. Risk category, which shall include options for technical, management, commercial, interdependency, or external risks.
PMO-RAID-3 | The Solution shall automatically assign a unique Risk ID for each risk identified and logged in a project. This Risk ID shall be composed of the following elements: | PMO | Phase 2
1. Project ID: To identify the associated project.
2. Sequential Risk Number: A unique number for each risk within the project (e.g., 001, 002).
The combination of the Project ID and the Sequential Risk Number shall ensure the uniqueness of the Risk ID across the entire portfolio and the Project Risk Database.
PMO-RAID-4 | The Solution shall create a Project Risk Database composed of the attributes described in PMO-RAID-2 in addition to the Unique Risk ID created as per PMO-RAID-3. | PMO | Phase 2
PMO-RAID-5 | The Solution shall automatically generate an entry in the Project Risk Database when a risk is identified in any project within the portfolio. It must also ensure that all entries in the Project Risk Database remain fully synchronized with the risk information recorded in individual projects risk registers. Any updates to the risk status, details, or ratings in the project risk registers shall be reflected in the Project Risk Database in real time. The risk database shall be imported or exported from MS Office tools. | PMO | Phase 2
PMO-RAID-6 | The Solution shall allow Project Manager to assign an owner to each identified risk. The assigned owner shall be a member of the project team. | PMO | Phase 2
PMO-RAID-7 | The Solution shall notify the team member upon being assigned as a risk owner. The notification shall be delivered through email and within the Solution and shall be sent immediately upon assignment. | PMO | Phase 2
PMO-RAID-8 | The Solution shall notify PMO Director, PMO Assistant, and all project stakeholders upon the identification and logging of a new risk within the project. The notification shall be delivered through email and within the Solution and shall be sent immediately upon identification of the risk. | PMO | Phase 2
PMO-RAID-9 | The Solution shall allow PMO Director to configure the scales and values used for assigning Probability (P) and Impact (I) ratings in qualitative risk analysis, along with corresponding color codes for each rating level. The Solution shall support configurable calculation rules for deriving a risk score (e.g., P × I) and enable mapping of risk scores to defined risk levels (e.g., Low, Medium, High), each with an associated configurable range and color for visual representation. | PMO | Phase 2
The Solution shall visually display the calculated risk scores and levels using a configurable risk matrix (heat map) to illustrate Probability vs. Impact with appropriate color coding for each risk.
PMO-RAID-10 | The Solution shall allow Project Manager to perform qualitative risk analysis by assigning /updating a probability (P) and an impact (I) rating to each identified risk in their project using the configured values as per PMO-RAID-9. | PMO | Phase 2
PMO-RAID-11 | Upon assigning the probability and impact to a risk, the Solution shall calculate the risk score for that risk according to the scoring scheme configured as per PMO-RAID-9. The calculated risk score shall determine the level of risk as (High, Moderate, Low) and assign the color coding according. | PMO | Phase 2
PMO-RAID-12 | The Solution shall allow Project Manager and Risk Owner to choose a response plan for each identified risk. This shall include the following: | PMO | Phase 2
1. A plan option (avoid, transfer, mitigate, share, or accept)
2. A description of the plan and the justification for choosing that option
3. Any associated Work Breakdown Structure (WBS) elements- if appliable.
4. The estimated duration associated with the plan- if appliable
5. The estimated costs associated with the plan- if appliable.
PMO-RAID-13 | The Solution shall allow Project Manager to calculate the overall risk score for their project, including the option to assign weights to individual risks. | PMO | Phase 2
The calculated total risk score shall determine the level of project risk, categorized as (High, Moderate, Low)
PMO-RAID-14 | The Solution shall provide PMO Director, ExCo Member, and PMO Assistant with the capability to extract a report – in PDF or Excel format -on portfolio risks.The report shall include the following information for each project: | PMO | Phase 2
1. Number of risks identified: Total count of identified risks.
2. Total risk score: The aggregate risk score for each project.
3. Risk details: Optional inclusion of specific risk IDs and descriptions, if applicable.
PMO-RAID-15 | The Solution shall enable Project Manager or the Risk Owner to update the risk status from "Opened" to "Occurred/materialized," "Closed," or "Transferred”. The transfer can be to an internal or external third party." | PMO | Phase 2
PMO-RAID-16 | The Solution shall notify interested Project Stakeholders of any updates made to a project risk. This notification shall be delivered via email immediately after the update, including a description, and its time and date. | PMO | Phase 2
PMO-RAID-17 | The Solution shall allow Project Stakeholders to view all open risks associated with the projects in which they are stakeholders. | PMO | Phase 2
RAID - Assumptions & Constraints
PMO-RAID-18 | The Solution shall automatically add the assumptions and constraints documented in the project charter upon initiation and assign a default status of “Not Verified Yet” in Assumption & Constraint Log | PMO | Phase 2
PMO-RAID-19 | The Solution shall allow Project Managers to document assumptions made in their projects by providing the following details: | PMO | Phase 2
1. Date the assumption was made
2. Category (technical, operational, financial)
3. Status (default initial status is “Not Verified Yet”
PMO-RAID-20 | The Solution shall automatically generate a unique ID for each assumption documented ensuring that the generated ID is unique across all projects within the portfolio. | PMO | Phase 2
PMO-RAID-21 | The Solution shall notify ExCo Sponsor and all Project Stakeholders upon the documentation of any assumption on their project. | PMO | Phase 2
PMO-RAID-22 | The Solution shall allow Project Manager to update the assumption's status from “Not Verified yet” to Verification in process, Verified as correct, Verified as incorrect. | PMO | Phase 2
PMO-RAID-23 | The Solution shall notify the ExCo Sponsor and all Project Stakeholders upon the status change of an assumption on their project. | PMO | Phase 2
PMO-RAID-24 | The Solution shall enable Project Manager to log constraints encountered in their projects, including the following details: | PMO | Phase 2
1. Description of the constraint
2. Date of identification
3. Type of constraint (e.g., Time, Cost, Scope, Resource, Safety)
4. Remediation for constraint (e.g. budget, resource)
PMO-RAID-25 | The Solution shall automatically notify PMO Director, ExCo Sponsor, and all Project stakeholders upon the logging of a new constraint. | PMO | Phase 2
RAID - Issues
PMO-RAID-26 | The Solution shall enable Project Managers to log issues encountered in their projects, including the following details: Description Date of identification Priority level (Low, Medium, High) Associated Risk ID if the issue is due to risk materialization. | PMO | Phase 2
PMO-RAID-27 | The Solution shall allow the Project Manager to assign an owner to each issue encountered. The assigned owner shall be a member of the project team. | PMO | Phase 2
PMO-RAID-28 | The Solution shall notify the team member upon being assigned as an issue owner, in accordance with PMO-RAID-013. The notification shall be delivered by email and shall be sent immediately upon assignment. | PMO | Phase 2
PMO-RAID-29 | The Solution shall automatically generate a unique ID for each issue upon logging ensuring that the generated ID is unique across all projects within the portfolio. | PMO | Phase 2
PMO-RAID-30 | The Solution shall allow Project Manager and Issue Owner to update the status of issues as they progress through resolution (e.g., Open, In Progress, Resolved, Closed). | PMO | Phase 2
PMO-RAID-31 | The Solution shall allow Project Stakeholders to view all the issues opened in the projects in which they are stakeholders. | PMO | Phase 2
PMO-RAID-32 | The Solution shall automatically notify PMO Director, ExCo Sponsor, and all Project stakeholders upon the logging of a new issue. | PMO | Phase 2
PMO-RAID-33 | The Solution shall send alerts to PMO Director, ExCo Sponsor, and all Project Stakeholders when the status of an issue changes or when updates are made by Project Manager or Issue Owner. | PMO | Phase 2
PMO-RAID-34 | The Solution shall provide the PMO Director with the capability to generate reports on all logged issues, including metrics such as total number of issues, resolution time, and outstanding issues per project. | PMO | Phase 2
PMO-RAID-35 | The Solution shall maintain a historical log of issue changes and resolutions for audit purposes. | PMO | Phase 2
PMO-RAID-36 | The Solution shall allow Project Managers to escalate issues to the PMO Director and ExCo Sponsor if they are not resolved within a specified timeframe. | PMO | Phase 2
PMO-RAID-37 | The Solution shall provide a mechanism for ExCo Sponsor to review escalated issues and assign additional resources if necessary. | PMO | Phase 2
PMO-RAID-38 | The Solution shall provide training materials and support resources to ensure all users are proficient in managing issues within the system. | PMO | Phase 2
RAID - Dependencies
PMO-RAID-39 | The Solution shall automatically add the dependencies documented in the project charter upon initiation in the dependency log. | PMO | Phase 2 - Medium Priority
PMO-RAID-40 | The Solution shall enable Project Managers to log interdependencies between their projects and other projects within the portfolio, including the following details: | PMO | Phase 2
Description of the interdependency
Date of identification
Type of interdependency (e.g., Resource sharing, Milestone alignment, Deliverable dependency)
Interdependent Project IDs
Interdependency type (Downstream, Upstream)
Impact assessment (e.g., high, medium, low)
PMO-RAID-41 | The Solution shall automatically generate a unique ID for each interdependency upon logging ensuring that the generated ID is unique across all projects within the portfolio. | PMO | Phase 2
PMO-RAID-42 | The Solution shall automatically notify the Project Manager(s) of other projects affected by the newly created dependency as per PMO-RAID-036 | PMO | Phase 2
PMO-RAID-43 | The Solution shall allow Project Manager to update the status of interdependencies as they evolve (e.g., Active, Resolved, Delayed). | PMO | Phase 2
PMO-RAID-44 | The Solution shall automatically open a risk in the risk register for any interdependency identified and notify Project Manager to update the risk. | PMO | Phase 2
PMO-RAID-45 | The Solution shall provide the PMO Director and PMO Assistant with the capability to generate reports on all logged interdependencies, including metrics such as total number of interdependencies, status distribution, and impact on project timelines. | PMO | Phase 2
Change Control Management
PMO-CCM-1 | The Solution shall allow any stakeholder (the requester) of a project to submit a change request with the provision of the following details: | PMO | Phase 2
1. Name of requester
2. Role in the project
3. Project ID
4. Project Name
5. A description of the proposed change.
6. The reason for the change.
7. The impact of the change on project scope, schedule, cost, safety, Risk, and resources.
PMO-CCM-2 | The Solution shall record all submitted change requests—across all projects—in a centralized master change log. Each entry shall include at minimum the project identifier, change request ID, date of submission, requesting user, and a default status of "Submitted." This logging shall occur automatically upon receipt of a new change request. | PMO | Phase 2
PMO-CCM-3 | The Solution shall allow Project Manager to review and update a change request with the outcome of the impact assessment for the proposed change with the ability to upload supporting documents. | PMO | Phase 2
PMO-CCM-4 | The Solution shall allow the requester to check the status of their submitted change requests, together with any comments or feedback provided by approvers and the date of the last status update. | PMO | Phase 2
PMO-CCM-5 | The Solution shall allow ExCo members to view changes requested at the projects they are sponsoring. | PMO | Phase 2
PMO-CCM-6 | The Solution shall enable authorized personnel from the Legal department to upload approved Change Orders to the project-assigned repository, providing confirmation of a successful upload that includes a timestamp and relevant metadata (such as the file name and uploader's name). | PMO | Phase 2
PMO-CCM-7 | The Solution shall allow authorized personnel from the Legal department to create a Change Order -using the Change Order Template - for the approved changes that require changes to contracts. | PMO | Phase 2
PMO-CCM-8 | The Solution shall allow ExCo member to sign Change Order Document created by Legal for the projects they are sponsoring. | PMO | Phase 2
PMO-CCM-9 | The Solution shall enable PMO Director and ExCo members to view all change requests within the project portfolio with the option to specify a starting date (month/year) and an ending date (month/year) to filter the displayed change requests based on the specified date range. | PMO | Phase 2
PMO-CCM-10 | The Solution shall route submitted change requests to designated approvers in accordance with a configurable Change Control Process workflow. The workflow shall support organization-specific approval sequences and capture the submission timestamp, requester information, and initial status ("Pending Approval"). Notifications shall be sent to approvers as part of the routing process. | PMO | Phase 2
PMO-CCM-11 | Upon the completion of their review of the change request, the Solution shall provide the approvers with the capability to: request additional information from the requestor if needed, approve the change request, reject the change request with a reason for rejection, or defer the decision on the change request for further consideration. | PMO | Phase 2
PMO-CCM-12 | The Solution shall provide tools to assess the risks associated with proposed changes. | PMO | Phase 2
PMO-CCM-13 | The Solution shall send automated notifications to stakeholders when a decision is made about a requested change (approved, rejected, or deferred). | PMO | Phase 2
PMO-CCM-14 | The Solution shall automatically update the status of the change request to the appropriate status based on predefined conditions in the workflow.Project Manager shall have the ability to manually update the status if necessary, overriding the system’s automatic update. The statuses include: | PMO | Phase 2
In Assessment
Under Project Manager/Team Review
Under Procurement Review
Under ExCo Review
Under Legal Review
Approved
Rejected
In Implementation
Completed
On Hold/Deferred.
Withdrawn
Reopened
PMO-CCM-15 | The Solution shall allow Project Manager to make the necessary updates to their project artifacts due to the approved changes. | PMO | Phase 2
Dashboard, Trending, and Reporting
PMO-DTR-1 | All components of the reports and dashboards specified in the requirements below shall be automatically generated, wherever possible, using data from integrated systems, with the option to manually add data if necessary. The vendor shall provide examples of automation workflows. The enclosed sample dashboard (main, monthly, weekly) provides a visual representation of all the requirements listed below). | PMO | Phase 2
PMO-DTR-2 | The Solution shall allow PMO Director to create and manage a database of Project Key Performance Indicators (KPIs). Each KPI must have the following information: | PMO | Phase 2
1. Name of the KPI
2. Description
3. Calculating formula (if applicable)
4. Target
5. Frequency of Measurement (weekly, monthly, quarterly, annually)
PMO-DTR-3 | The Solution shall allow PMO Director to configure the traffic light status (Green, Yellow, Red) for scope, schedule, budget, resources, safety, and risk, as well as overall project status, for all projects or specific projects, based on the appropriate KPI/metric for each element. If the traffic light status is not explicitly set for a project, it shall inherit the configuration set for the portfolio. | PMO | Phase 2
PMO-DTR-4 | The Solution shall calculate the overall portfolio percentage progress based on the percentage progress and duration of each project. This overall percentage progress must be automatically updated whenever the percentage progress or duration of a project is updated, or a new project is added to the portfolio. | PMO | Phase 2
PMO-DTR-5 | The Solution shall calculate the percentage of the budget utilized across the entire portfolio based on the total approved budget and the total actual costs. This percentage must be automatically updated whenever a new project is added (adding an approved budget for that project) and/or expenses are posted to projects in Master Project Cost Register. | PMO | Phase 2
PMO-DTR-6 | The Solution shall enable PMO Director to automatically create a project health matrix at any time for all active projects. This matrix shall display the number of projects with issues (Yellow & Red) reported, in the areas of scope, schedule, budget, resources, safety, and risk. Additionally, the matrix shall include plans to address those issues. | PMO | Phase 2
PMO-DTR-7 | The Solution shall allow PMO Director to create a two-dimensional chart displaying the monthly status of the approved budget, contingency, budget at completion (BAC), actual cost (AC), and estimate to complete (ETC). The chart should be aggregated by each department and for all active projects in the portfolio. The chart must include axis label and legends for clarity. | PMO | Phase 2
PMO-DTR-8 | The Solution shall allow ExCo Sponsor and Departmental Director to create a two-dimensional column chart displaying the status of the approved budget, contingency, budget at completion (BAC), actual cost (AC), and estimate to complete (ETC) for all the projects in their departments, with the capability to specify the starting date and ending date. | PMO | Phase 2
PMO-DTR-9 | The Solution shall provide PMO Director with the capability to extract monthly trends- in a line graph format- of percentage progress for all projects in the portfolio, with the ability to specify the starting month and ending month. | PMO | Phase 2
PMO-DTR-10 | The Solution shall provide PMO Director with the capability to extract monthly trends -in a line graph format-of CapEx hours utilized for all projects in the portfolio, projects outside the portfolio -Non-PMO Project, and for Total projects, with the ability to specify the starting month and ending month. | PMO | Phase 2
PMO-DTR-11 | The Solution shall provide PMO Director with the capability to extract monthly trends- in a line graph format- of number of EHS-related issues for all projects in the portfolio, with the ability to specify the starting month and ending month. | PMO | Phase 2
PMO-DTR-12 | The Solution shall allow PMO Director to generate a monthly report that outlines major accomplishments for the current month and major activities planned for the following month for all projects in the portfolio for a specified month/year. | PMO | Phase 2
PMO-DTR-13 | The Solution shall enable PMO Director to generate a monthly report that details major milestones for the current month, including their status (Missed or Hit) and the impact of any missed milestones. Additionally, the report shall include major milestones planned for the following month along with their due dates for all projects in the portfolio for a specified month/year. | PMO | Phase 2
PMO-DTR-14 | The Solution shall provide PMO Director with the capability to extract a monthly trend, in a line graph format, of the Cost Performance Index (CPI) and Schedule Performance Index (SPI) for a specific project, all projects in the portfolio, the average CPI and SPI for the portfolio, or a combination of these options. The Solution shall allow PMO Director to specify the starting month/year and ending month/year. | PMO | Phase 2
PMO-DTR-15 | The Solution shall enable the PMO Director to generate reports on metrics and KPIs, including the following information: | PMO | Phase 2
KPI
Description
Target
Measurement Frequency
Actual Value
Start and End Date
The PMO Director shall have the option to select which projects to include in the report based on their status (Initiated, In Progress, Completed, Pended, Cancelled).
PMO-DTR-16 | The Solution shall allow PMO Director to generate monthly reports that provide trends and insights across projects. These reports shall include, but are not limited to, trends on: | PMO | Phase 2
1. Percentage of Progress: including percentage progress for all the projects and the overall percentage progress
2. Overall Percentage of Progress
3. Cost Performance Indicator (CPI) and Schedule Performance Indicator (SPI)
4. CapEx Hours Expended (In PMO projects, non-PMO projects, and All projects)
5. EHS-Related Incidents/Issues
6. Overall Project Health, including issues related to scope, schedule, budget, resources, safety, and risk
The PMO Director shall have the option to specify the month and year for the report, as well as select which projects to include based on their status (Initiated, In Progress, Completed, Pended, Cancelled).
PMO-DTR-17 | The Solution shall enable PMO Director to generate a monthly report detailing all active projects in the portfolio for a specified month/year. This report shall include the following information: | PMO | Phase 2
1. Project Name
2. Department
3. Duration (in months)
4. Percentage Complete
5. Approved Budget
6. Percentage of Budget Used
7. Project Health (indicated as Green, Yellow, or Red), covering:
7.1. Overall Status
7.2. Scope
7.3. Budget
7.4. Resources
7.5. Safety
7.6. Risk
8. Key Performance Indicators (KPIs), including:
9. Cost Performance Index (CPI)
10. Schedule Performance Index (SPI)
11. Variance at Completion (VAC)
12. Number of Incidents/Issues
13. Number of Change Orders
14. Internal Resource Utilization (in hours)
15. Number of non-compliances
16. Gantt Chart covering the specified month through to the project's end month
PMO-DTR-18 | The Solution shall allow PMO Director to generate a monthly report that details cost and budgeting information for all projects in the portfolio for a specified month/year. This report shall include the following information: | PMO | Phase 2
1. Project Name
2. Department
3. Project Account Number
4. Percentage Complete
5. Budget:
5.1. Approved Amount
5.2. Date Approved
5.3. Approved Authority
6. Percentage Spent
6.1. Project Spend
6.2. Non-Labor: Purchases
6.3. Labor: CapEx Labor/Salary
6.4. Total
7. Contracts:
7.1. Contract Number
7.2. Contract Date
7.3. Contractor/Vendor
7.4. Contract Amount
7.5. Amount Paid to Date
7.6. Remaining Balance
8. Estimated Monthly Payment Schedule (Forecast- for at least 6 months)
PMO-DTR-19 | The Solution shall enable PMO Director to generate a report detailing all active procurement activities across all projects in the portfolio. This report shall include the project ID, project name, procurement description, and the progression through all the stages of the procurement workflow with the status of each stage (Not Started, In Progress, Completed). | PMO | Phase 2
PMO-DTR-20 | The Solution shall provide PMO Director with the capability to generate a comprehensive monthly dashboard that consolidates the components mentioned in PMO-DAT-4 through PMO-DAT-19. The Solution shall provide the option to export the consolidated dashboard into a pre-formatted PowerPoint Slides, with each major component presented clearly for reporting and presentation purposes. | PMO | Phase 2
PMO-DTR-21 | The Solution shall provide the option to export the consolidated dashboard into a pre-formatted PowerPoint Slides, with each major component presented clearly for reporting and presentation purposes. The Solution shall allow Project Manager to generate and customize a monthly dashboard for each of their projects. The dashboard must include the following components: | PMO | Phase 2
1. Month Covered/Year
2. Project Description
3. Start and End Date
4. Progress Percentage: Displays the overall progress of the project as a percentage.
5. CapEx Hours Expended for the Month: Shows the total Capital Expenditure (CapEx) hours utilized during the month.
6. Budget Approved
7. Percentage of Budget Utilized Up to date: Displays the percentage of the project budget that has been used to date.
8. Project Overall Status: Indicates the project's overall status using traffic light indicators (Green, Yellow, Red).
9. Project Status by Key Areas: Shows the status of the project in the following areas using traffic light indicators (Green, Yellow, Red):
· Scope
· Schedule
· Budget
· Resources
· Safety
· Risk
10. Project Life Cycle Phase: Displays the current phase of the project life cycle (Initiating, Planning, Executing, or Closing).
11. Percentage of Progress in Each Phase: Shows the percentage of progress within each phase of the project life cycle.
12. Major Accomplishments/Activities for the month: Lists significant achievements or activities completed during the month.
13. Major Activities Planned for Next Month: Details of key activities scheduled for the upcoming month.
14. Issues or Impediments Reported This Month: Lists issues or impediments encountered during the month along with resolution plans.
15. Risks Materialized This Month: Details any risks that materialized during the month and their impact on the project.
16. New Risks Identified This Month: Lists new risks identified during the month along with their response plans.
17. Help Needed from PMO/ExCo Sponsor: Specifies any assistance required from the PMO or Executive Sponsor.
PMO-DTR-22 | The Solution shall allow Project Manager to generate and customize a weekly dashboard for each of their projects on. The dashboard must be created on Friday and should cover all work completed on the project from the previous Saturday through to that Friday. The dashboard must include the following components: 1. Week Covered (Start Date - End Date) 2. Progress Percentage: Displays the overall progress of the project as a percentage. 3. CapEx Hours Expended for the Week: Shows the total Capital Expenditure (CapEx) hours utilized during the week. 4. Percentage of Budget Utilized Up to date: Displays the percentage of the project budget that has been used to date. 5. Project Overall Status: Indicates the project's overall status using traffic light indicators (Green, Yellow, Red). 6. Project Status by Key Areas: Shows the status of the project in the following areas using traffic light indicators (Green, Yellow, Red): · Scope · Schedule · Budget · Resources · Safety · Risk 7. Project Life Cycle Phase: Displays the current phase of the project life cycle (Initiating, Planning, Executing, or Closing). 8. Percentage of Progress in Each Phase: Shows the percentage of progress within each phase of the project life cycle. 9. Major Accomplishments/Activities for the Week: Lists significant achievements or activities completed during the week. 10. Major Activities Planned for the Next Week: Details of key activities scheduled for the upcoming week. 11. Issues or Impediments Reported This Week: Lists issues or impediments encountered during the week along with resolution plans. 12. Risks Materialized This Week: Details any risks that materialized during the week and their impact on the project. 13. New Risks Identified This Week: Lists new risks identified during the week along with their response plans. 14. Help Needed from PMO/ExCo Sponsor: Specifies any assistance required from the PMO or Executive Sponsor. The Solution shall provide the option to export the consolidated dashboard into a pre-formatted PowerPoint Slides, with each major component presented clearly for reporting and presentation purposes. | PMO | Phase 2
PMO-DTR-23 | The Solution shall allow Project Manager to automatically create progress and status reports for their projects based on the Project Progress & Status Report Template (PMO-DOC-008), with the option to manually add data that cannot be generated automatically. | PMO | Phase 2
PMO-DTR-24 | The Solution shall notify all Project Stakeholders when a weekly or monthly dashboard is generated for the projects in which they are stakeholders. | PMO | Phase 2
PMO-DTR-25 | The Solution shall notify ExCo Members and Project Managers when PMO Monthly dashboard is generated as per PMO-DAT-20 | PMO | Phase 2
PMO-DTR-26 | The Solution shall allow Executive Committee (ExCo) members to view the weekly dashboard for a specific project with the ability to specify the week (first, second, third, fourth, or fifth), month, and year when viewing the dashboard. | PMO | Phase 2
PMO-DTR-27 | The system shall allow Executive Committee (ExCo) members to view the monthly PMO dashboard (Aggregate of the all the projects on the PMO) with the ability to specify the month and year when viewing the dashboard. | PMO | Phase 2
PMO-DTR-28 | The Solution shall enable ExCo Sponsor to retrieve all or any of the following information for a specific project they are sponsoring at any time: 1. Overall Project Status: Displays the project’s overall status using traffic light indicators (Green, Yellow, Red). 2. End Date – according to the latest baseline. 3. Percentage of Progress. 4. Percentage of Budget Utilized. 5. Number of Resources Assigned to the Project. 6. Total Number of CapEx Hours Spent. 7. Current Phase within the Project Life Cycle (PLC). 8. Percentage of Progress within each phase of the PLC. 9. Actual Cost (AC). 10. Estimate to Complete (ETC). 11. Variance at Completion (VAC). 12. Cost Performance Index (CPI). 13. Schedule Performance Index (SPI). 14. Number of EHS-Related Issues and Their Categorization, including: a. Lost Time Injury Frequency Rate (LTIFR) b. Lost Time Injury Severity Rate (LTISR) c. Near-Miss Incidents d. Days Away on Restricted or Transferred Duty (DART) Rate 15. Status of Scope, Schedule, Budget, Resources, Safety, and Risks using indicators: Green, Yellow, and Red. 16. The number of risks identified in the project along with their risk scores. 17. Overall risk score of the project. 18. Active Dependencies. 19. Number of contractors/vendors involved in the project. 20. Number of Change Requests submitted. 21. Total count of non-compliances with the PMO Project Management Framework. | PMO | Phase 2
PMO-DTR-29 | The Solution shall enable Project Manager to retrieve all or any of the following information for a specific project they oversee at any time: 1. Overall Project Status: Displays the project’s overall status using traffic light indicators (Green, Yellow, Red). 2. End Date – according to the latest baseline. 3. Percentage of Progress. 4. Percentage of Budget Utilized. 5. Number of Resources Assigned to the Project. 6. Total Number of CapEx Hours Spent. 7. Current Phase within the Project Life Cycle (PLC). 8. Percentage of Progress within each phase of the PLC. 9. Actual Cost (AC). 10. Estimate to Complete (ETC). 11. Variance at Completion (VAC). 12. Cost Performance Index (CPI). 13. Schedule Performance Index (SPI). 14. Number of EHS-Related Issues and Their Categorization, including: a. Lost Time Injury Frequency Rate (LTIFR) b. Lost Time Injury Severity Rate (LTISR) c. Near-Miss Incidents d. Days Away on Restricted or Transferred Duty (DART) Rate 15. Status of Scope, Schedule, Budget, Resources, Safety, and Risks using indicators: Green, Yellow, and Red. 16. Number of risks identified in the project along with their risk scores. 17. Overall risk score of the project. 18. Active Dependencies. 19. Number of contractors/vendors involved in the project. 20. Number of Change Requests submitted. 21. Total count of non-compliances with the PMO Project Management Framework. | PMO | Phase 3
PMO-DTR-30 | The Solution shall enable Project Manager to review and generate reports for all contracts associated with each of their projects. Each report shall include the following details for each contract: 1. Contract Number 2. Contractor/Vendor Name 3. Contract Date 4. Original Contract Sum 5. Sum of Change Orders 6. Current Contract Sum 7. Amount Paid to Date 8. Remaining Balance 9. Monthly Drawdown Schedule | PMO | Phase 2
PMO-DTR-31 | The Solution shall enable ExCo Member, PMO Director, and designated Project Stakeholders from procurement and legal to review and generate reports for all contracts associated with any project within the portfolio. Each report shall include the following details for each contract: 1. Contract Number 2. Contractor/Vendor Name 3. Contract Date 4. Original Contract Sum 5. Sum of Change Orders 6. Current Contract Sum 7. Amount Paid to Date 8. Remaining Balance 9. Monthly Drawdown Schedule | PMO | Phase 2
PMO-DTR-32 | The Solution shall allow PMO Director to obtain the following information for all projects in the portfolio at any given time: 1. Total number of projects 2. Average percentage of progress 3. Average percentage of budget utilized 4. Number of resources allocated to projects 5. Total number of CapEx hours spent 6. Number of projects by department (Finance & Procurement, HUB, Infrastructure, IT, Legal, Operations, Toll Operations) 7. Number of projects categorized by status (Initiated, In Progress, Completed, Pended, Cancelled) 8. Number of projects in each phase of the Project Life Cycle (PLC) 9. Total approved budget 10. Total actual cost (AC) 11. Total estimate to complete (ETC) 12. Total variance at completion (VAC) 13. Average Cost Performance Index (CPI) 14. Average Schedule Performance Index (SPI) 15. Total number of EHS-related issues and their categorizations, including: · Lost Time Injury Frequency Rate (LTIFR) · Lost Time Injury Severity Rate (LTISR) · Near-Miss Incidents · Days Away on Restricted or Transferred Duty (DART) Rate 16. Number of projects classified by status indicators: Green, Yellow, and Red for Scope, Schedule, Budget, Resources, Safety, and Risks 17. Total count of non-compliances with the PMO Project Management Framework. | PMO | Phase 2
PMO-DTR-33 | The Solution shall enable Resource Manager to generate a report detailing their resource allocation to projects, including the following information: 1. Name of Resource 2. Project Name 3. Percentage of Allocation 4. Start and End Dates of Allocation | PMO | Phase 2
PMO-DTR-34 | The Solution shall provide up-to-date information on resource availability, current workload, and project dependencies, facilitating informed decision-making with regard to resource management across ITR. | PMO | Phase 2
PMO-DTR-35 | The Solution shall allow PMO Assistant to view and/or generate reports in accordance with the authority delegated by the PMO Director. | PMO | Phase 2
PMO-DTR-36 | The Solution shall enable Project Stakeholders to view and/or generate a report detailing their assigned activities and their ownership of risks and issues across all projects in the portfolio. | PMO | Phase 2
PMO-DTR-37 | The Solution shall allow PMO Director, ExCo Member, and Project Manager to generate the following reports based on access authority 1. Issue Report- based on Issue Log 2. Risk Report – based on Risk Register 3. Financial Report – based on Master Project Cost Register 4. Milestone Report 5. Resource allocation report 6. CapEx Hours reported for specific project or several projects 7. Change Requests (Orders)
PMO-DTR-38 | The Solution shall allow Project Manager to view all projects assigned to them across the portfolio, with the capability to drill down into individual project details. The drill-down view shall include, at a minimum: 1. Project Name and ID 2. Current Phase and Status 3. Major activities and Status 4. Key Milestones and Dates 5. Budget Summary (Allocated vs. Spent) 6. CapEx Hours Logged 7. Risk and Issue Summary 8. Stakeholder Engagement Status | PMO | Phase 2
PMO-DTR-39 | The Solution shall allow ExCo Member and Project Stakeholder a to customize their dashboard views based on their preferences and roles. | PMO | Phase 2
PMO-DTR-40 | The Solution shall provide automated reporting features that allow for the scheduling of specific reports to be generated and delivered to Project stakeholders at designated dates and times. | PMO | Phase 2
PMO-DTR-41 | The Solution shall provide reporting capabilities to summarize lessons learned across projects, highlighting key insights and trends for stakeholders. | PMO | Phase 2
PMO-DTR-42 | The Solution shall grant ExCo Member role the ability to export reports in PDF format for any information related to any project within the PMO including options for customizing the content of the reports before exporting, such as selecting date ranges or specific metrics. | PMO | Phase 2
PMO-DTR-43 | The Solution shall support interactive drill-down functionality within dashboards, allowing authorized users to navigate from the portfolio level to associated projects and further to individual activities. Drill-down access shall be governed by role-based access controls (RBAC), ensuring users can only view data for entities they are permitted to access. | PMO | Phase 2
PMO-DTR-44 | The Solution shall provide reporting features to generate insights on change requests/orders, such as: number of requests submitted, approved, and rejected; time taken for approvals; and Common reasons for changes.
PMO-DTR-45 | The Solution shall provide a standardized, filterable, and exportable report of completed projects within the portfolio to enable the PMO to monitor project performance, compliance, and delivery outcomes. The report shall include the following details with a configurable color-coding for metrics: 1. Project Identification · Project ID · Project Name · Project Manager · Month Completed 2. Stakeholder Evaluation · Stakeholder Satisfaction Index (SSI) o Displayed as a percentage o Flag values below threshold 3. Financial Performance · Approved Budget · Contractor/Vendor Name · Original Contract Value · Change Orders (number and/or brief summary) · Adjusted Contract Value (Original + Change Orders) · Other Expenses · Actual Cost at Completion · % Budget Utilized at Completion (Actual Cost ÷ Approved Budget × 100) · Variance at Completion (Approved Budget – Actual Cost) 4. Schedule Performance · Planned End Date · Actual End Date · Schedule Variance at Completion (Planned – Actual Days) 5. KPI Dashboard Integration · Budget Adherence Rate (% of projects within budget) · On-Time Completion Rate (% of projects finished on or before planned end date) · Average SSI across completed projects · Average Variance at Completion · % of Projects with Change Orders 6. Functional Features · Automated calculations for derived metrics · Visual benchmarks using icons or color indicators (✓ / ⚠️ / ✖) · Export options: PDF, Excel · Filtering/sorting by month/ year, business unit, or project manager. 7. Automation & Notifications · The report shall be auto generated on a monthly schedule (configurable generation date). · The Solution shall notify authorized stakeholders (e.g., PMO Director, ExCo Member, Departmental Director/Manager) when the report is generated or updated. | PMO | Phase 2
PMO-DTR-46 | The Solution shall allow PMO Director, ExCo Members, and Procurement Manager to generate a report of all invoices and their statuses across all projects in the portfolio. The report shall include key fields such as invoice number, project name, vendor/contractor, invoice amount, invoice date, due date, payment status, and comments. The Solution shall also provide filtering options by project, vendor/contractor, invoice status, and date range. | PMO | Phase 2
Closing
PMO-CLO-1 | The Solution shall facilitate the collection and documentation of final approvals from key stakeholders to formally close the project, utilizing configurable built-in forms such as Deliverable Acceptance Form, Substantial Completion Certificate, and Final Project Completion Form. | PMO | Phase 2
PMO-CLO-2 | The Solution shall enable the reconciliation of all financial transactions related to the project, including final payments, invoices, retainages, and budget variances. | PMO | Phase 2
PMO-CLO-3 | The Solution shall allow for a final compliance check to ensure all regulatory and organizational requirements have been met before closure. | PMO | Phase 2
PMO-CLO-4 | The Solution shall provide a feature to log lessons learned during the project, making them accessible for future reference and continuous improvement. | PMO | Phase 2
PMO-CLO-5 | The Solution shall facilitate the collection of stakeholder feedback by supporting surveys with configurable questions. The surveys shall be triggerable automatically or manually during the project closure phase, support optional anonymous responses, and enable aggregation, storage, and reporting of survey results to inform future project management improvements. | PMO | Phase 2
PMO-CLO-6 | The Solution shall allow the PMO Director to calculate the Stakeholder Satisfaction Index (SSI) for the project based on the survey results collected as per PMO-CLO-10, applying configurable weighting to each survey question or response. | PMO | Phase 2
PMO-CLO-7 | Upon the calculation of the Stakeholder Satisfaction Index (SSI) as per PMO-CLO-11, the Solution shall automatically update the average SSI for all projects completed under the PMO. | PMO | Phase 2
PMO-CLO-8 | The Solution shall allow Project Managers to generate a comprehensive project closure report using a built-in template that includes project performance metrics, lessons learned, and final budget details. | PMO | Phase 2
PMO-CLO-9 | The Solution shall enable the scheduling and documentation of a final performance review meeting to evaluate project outcomes against objectives. | PMO | Phase 2
PMO-CLO-10 | The Solution shall support the transition of project deliverables to operational teams, including the necessary training and documentation. | PMO | Phase 2
PMO-CLO-11 | The Solution shall allow Project Manager to archive all project-related documents in a centralized repository for future access and audits. | PMO | Phase 2
PMO-CLO-12 | The Solution shall provide functionality to allow Project Manager to release project resources (human, equipment, etc.). | PMO | Phase 2
PMO-CLO-13 | The Solution shall enable the documentation, reporting, and handover of any outstanding issues or risks remaining post-closure, including recommended actions for resolution or response plans. | PMO | Phase 2
PMO-CLO-14 | The Solution shall allow the Procurement Manager to document vendor/supplier evaluations using a structured scorecard assessment based on predefined criteria (e.g., quality, timeliness, safety, cost control, responsiveness). The Solution shall have a configurable workflow for multiple users to participate in the evaluation. Upon finalization of the evaluation, the Solution shall automatically notify Project Manager and PMO Director. | PMO | Phase 2
PMO-CLO-15 | The Solution shall provide a project closure checklist to ensure all necessary steps are completed before the project is officially closed. | PMO | Phase 2
PMO-CLO-16 | The Solution shall allow PMO Director to perform and document a gate review of the project closure phase, verifying completion of all deliverables, contractual obligations, lessons learned, and administrative closeout activities, before enabling notification to all stakeholders regarding the official project closure. | PMO | Phase 2
PMO-CLO-17 | The Solution shall automatically notify all project stakeholders of the project closure, including summaries of key outcomes and any outstanding issues, only after the PMO Director has completed and approved the project closure gate review. | PMO | Phase 2
PMO-CLO-18 | The Solution shall maintain an audit trail of all closing activities and decisions for accountability and transparency. | PMO | Phase 2
PMO-CLO-19 | The Solution shall support scheduling and conduct a post-implementation review to assess the long-term effectiveness and impact of the project. | PMO | Phase 2
PMO-CLO-20 | The Solution shall automatically update the PMO project database upon project closure with the following actual completion data: Actual End Date, Actual Duration, Actual Cost (AC), Stakeholder Satisfaction Index (SSI), Total CapEx Hours used, Final Project Status (e.g., "Completed and Closed" or "Cancelled and Closed"), and any associated Notes, Remarks, or Comments. | PMO | Phase 2
Strategic Planning and Portfolio Management
PMO-SPPM-1 | The Solution shall allow a Business Case Owner to create a business case for a new initiative using a built-in, configurable business case template. The template shall include, at a minimum, fields for: problem or opportunity statement, strategic alignment, analysis of alternative options with associated cost estimates, resource requirements, proposed timelines, risk assessment, expected benefits, and return on investment (ROI). The Solution shall support the routing of the completed business case through a configurable, multi-level approval workflow aligned with the ITRCC governance framework. | PMO | Phase 3
PMO-SPPM-2 | The Solution shall maintain a centralized repository of all submitted business cases, including their approval status, version history, submission date, and associated documents. Authorized users shall be able to search, filter, and export this data based on lifecycle stage, business unit, strategic domain, or funding request. | PMO | Phase 3
PMO-SPPM-3 | The Solution shall allow Board Members and ExCo members to securely access all submitted business cases. The system shall display key evaluation data such as strategic fit, estimated ROI, compliance impact, funding required, and risk exposure to facilitate informed evaluation and prioritization. | PMO | Phase 3
PMO-SPPM-4 | The Solution shall support a multi-criteria scoring model configurable by Board or ExCo. This model shall allow ExCo and Board members to rate business cases across predefined criteria (e.g., value contribution, risk, urgency, funding need). The Solution shall automatically compute aggregate scores and rankings to enable prioritization. | PMO | Phase 3
PMO-SPPM-5 | The Solution shall provide dashboards and reports showing prioritized lists of business cases, funding gaps, and what-if scenarios based on different funding levels. This enables decision-makers to select initiatives that provide the highest strategic value within available budgets. | PMO | Phase 3
PMO-SPPM-6 | The Solution shall integrate selected and approved business cases into the portfolio planning and budgeting modules, ensuring seamless transition from strategic intake to project classification and initiation. | PMO | Phase 3
Phase 3 – Strategic Sourcing and Contract Management. - Phase 3 shall not be priced.
Contract Management - Contract Authoring
ERP-S2C-121 | The solution shall provide self-service contract requests and record creation based on approvals by authorized personnel. | S2C | Phase 3
ERP-S2C-122 | The solution shall be capable of creating at least 10 different types of ITR branded and client-side configured contracts. | S2C | Phase 3
ERP-S2C-123 | The solution shall provide on-line creation of contracts and web-based request form for filling data and conditional variables | S2C | Phase 3
ERP-S2C-124 | The solution provides contract and document templates and “wizards” by contract type. | S2C | Phase 3
ERP-S2C-125 | The solution shall provide pre-approved clauses and language libraries, including fallback clauses. | S2C | Phase 3
ERP-S2C-126 | The solution provides for a "Configurable View" to expedite execution of tasks. | S2C | Phase 3
ERP-S2C-127 | The solution shall provide descriptions to each document uploaded to the system that can be added by authorized users. | S2C | Phase 3
ERP-S2C-128 | The Solution shall provide the Procurement Manager with the capability to acknowledge receipt of the Procurement Request (PR) and to add a customized message relevant to the request. | S2C | Phase 3
ERP-S2C-129 | The Solution shall provide the Procurement Manager with the capability to assign PR to a responsible Buyer, update the status of Procurement Request (PR) as well as adding any additional information. The available status options must include Received, In Process, Approved, Pending, and Rejected. | S2C | Phase 3
ERP-S2C-130 | The Solution shall allow User to check the status of Procurement Requests (PRs) that they have submitted. | S2C | Phase 3
ERP-S2C-131 | Upon the Procurement Request (PR) status changing to “Approved,” the Solution shall notify User that their request has been approved. | S2C | Phase 3
ERP-S2C-132 | The S2C Solution shall allow Users to submit a Procurement Request to initiate a new procurement within the S2C. The request must include the following details: 1. SOW 2. Purchase Description, 3. Department (F&P, HUB, INF, IT, Legal, OPS, Toll Ops), 4. Username 5. Approved Budget, 6. Date Budget approved, 7. Budget Approved Authority -Approved capex budget -Approved OpEx budget -ExCo delegated authority -CEO delegated authority 8. Delivery Date, 9. Contract Number (if known) 10. Vendor/Supplier Name (if known) 11. Attachments (approved MS office and Adobe format) | S2C | Phase 3
Contract Management - Contract Templates
ERP-S2C-133 | The Contract solution shall dynamically assign stakeholders and role-based user rules. | S2C | Phase 3
ERP-S2C-134 | The Contract solution have Risk level configuration to apply pre-approved terms. | S2C | Phase 3
ERP-S2C-135 | The Contract solution Identify data fields in a contract template and establish business rules for the fields. | S2C | Phase 3
ERP-S2C-136 | The Contract solution shall use Microsoft Word to author/edit a contract and sync back. | S2C | Phase 3
ERP-S2C-137 | The Contract solution shall use Contract templates or Clause library for including clause inclusion during authoring and negotiation. | S2C | Phase 3
ERP-S2C-138 | The Contract solution shall highlight specific clauses or sections in templates and establish events and workflows for the clauses. | S2C | Phase 3
ERP-S2C-139 | The Contract solution shall support users for both internal and external users. | S2C | Phase 3
ERP-S2C-140 | The Contract solution shall accept or reject redlining by internal and external users. | S2C | Phase 3
ERP-S2C-141 | The Contract solution shall manage and separately track multiple negotiations with same business user. | S2C | Phase 3
ERP-S2C-142 | The Contract solution shall notify internal users in any contract changes done by external stakeholders. | S2C | Phase 3
ERP-S2C-143 | The Contract solution shall allow authorized users to assemble a contract draft by completing a Question & Answer template. | S2C | Phase 3
Contract Management - MS Office Integration
ERP-S2C-144 | The Contract solution shall have Native integration capabilities with MS Office templates. The Proposer shall describe any exceptions in its proposals. | S2C | Phase 3
ERP-S2C-145 | The Contract solution shall interface/import MS Word, PDF and other documents. | S2C | Phase 3
ERP-S2C-146 | The Contract solution shall use MS-Word for editing contract. | S2C | Phase 3
ERP-S2C-147 | The Contract solution shall Automatically import, and reconciling revisions using Microsoft Word and identify changes. | S2C | Phase 3
ERP-S2C-148 | The Contract solution shall track redlines, term changes, and comments entered using Microsoft Word. | S2C | Phase 3
ERP-S2C-149 | The Contract solution shall access clause libraries from Microsoft Word (if configured). | S2C | Phase 3
Contract Management - Contract Negotiations
ERP-S2C-150 | The Contract solution shall support contract negotiations and track deviations from based contracts. | S2C | Phase 3
ERP-S2C-151 | The Contract solution shall provide negotiated redline contract clauses/terms to be merged into the original contract. | S2C | Phase 3
ERP-S2C-152 | The Contract solution shall send notifications to users immediately in case of deviation from terms/clauses. | S2C | Phase 3
ERP-S2C-153 | The Contract solution shall disallow users from editing non-negotiable clauses, terms and rates. | S2C | Phase 3
ERP-S2C-154 | The Contract solution shall provide version control and version control logs for changes of contracts by vendor and over the last 10 years. | S2C | Phase 3
ERP-S2C-155 | The Contract solution shall allow negotiation in MS Word among stakeholders without the need to log into the system. | S2C | Phase 3
ERP-S2C-156 | The Contract solution shall send email with a Word document attached to the counterparty. | S2C | Phase 3
ERP-S2C-157 | The Contract solution shall provide redlining, audit trail, version tracking and document check-in and check-out capabilities. | S2C | Phase 3
ERP-S2C-158 | The Contract solution shall track key relationships among entities (e.g., Parent-Subsidiary) and display those relationships. | S2C | Phase 3
ERP-S2C-159 | The Contract solution shall capture logs- recorded and maintained within the contract solution module. | S2C | Phase 3
Contract Management - Workflow Approval
ERP-S2C-160 | The Contract solution shall enforce a standard workflow and/or status. The Contract solution workflows shall be configured by users to ensure internal and external parties can be in designated roles and all workflows shall be configured by the Company without knowledge in coding. The Proposer shall describe its workflow configuration in its Proposal. | S2C | Phase 3
ERP-S2C-161 | The Contract solution shall provide configurable user profiles for collaboration among contract management. | S2C | Phase 3
ERP-S2C-162 | The Contract solution shall implement “custom” business rules in the application. | S2C | Phase 3
ERP-S2C-163 | The Contract solution shall provide workflow management - allow events to set trigger alerts/review cycles and/or approval cycles. | S2C | Phase 3
ERP-S2C-164 | The Contract solution shall send emails for approvals based on configured workflow stages and required approval levels as defined in the Contract solution. The workflows shall be configurable based on established Company minimum and maximum levels. | S2C | Phase 3
ERP-S2C-165 | The Contract solution shall escalate Delegation of Authority within approval process. The Delegation of Authority is the Company policy for expenditure based on role and will be configured with the selected Vendor during design. | S2C | Phase 3
ERP-S2C-166 | The Contract solution shall provide automated workflow/email alerts for specified contract related dates, | S2C | Phase 3
ERP-S2C-167 | The Contract solution shall provide notifications and automatic contract renewal options to buyer and vendor. | S2C | Phase 3
Contract Management - Administration and Management
ERP-S2C-168 | The Contract solution shall link to a central contract repository with master and supplemental agreements. | S2C | Phase 3
ERP-S2C-169 | The Contract solution shall group contracts in hierarchy in contract repository. | S2C | Phase 3
ERP-S2C-170 | The Contract solution shall manage and store partner information and manage user authorization | S2C | Phase 3
ERP-S2C-171 | The Contract solution shall capture, track and measure service level agreements and operations and maintenance contracts. | S2C | Phase 3
ERP-S2C-172 | The Contract solution shall have an audit log for all contracts including all updates made and user made by and dates made. | S2C | Phase 3
ERP-S2C-173 | The Contract solution shall have post contract-activation stages, that attach related documents to contracts during development, negotiations and archival stages. | S2C | Phase 3
ERP-S2C-174 | The Contract solution shall provide alerts for contract renewals/amendments. | S2C | Phase 3
ERP-S2C-175 | The Contract solution shall describe abilities and features that our power users will have to create and modify templates for contract creation. | S2C | Phase 3
ERP-S2C-176 | The Contract solution shall maintain and update contract types including keeping a history of the contract types. | S2C | Phase 3
ERP-S2C-177 | The Contract solution shall create, maintain and archive amendments for each contract in accordance with the retention requirements. | S2C | Phase 3
ERP-S2C-178 | The Contract solution shall make mass changes or modify header field values on contracts from one central place. | S2C | Phase 3
ERP-S2C-179 | The Contract solution mass re-assign or transfer contracts from one user to another user due to organizational changes or user departure. | S2C | Phase 3
Contract Management Integration Requirements
ERP-S2C-210 | The S2C solution shall integrate with the Accounting and Finance module of ERP system to extract the following: 1. Pull Budget information from Finance Module to S2C 2. Pull Account Number information, Asset Classification (if applicable) and Capex Project ID from Finance Module to S2C 3. Invoice and Payment status from Finance Module to S2C | S2C | Phase 3
ERP-S2C-211 | The S2C solution shall integrate with the ERP system to communicate data related to the following procurement elements: 1. Purchase Orders (POs): Detailed information regarding purchase orders, including PO number, supplier details, and status. 2. Supplier/vendor Details: Payment terms, W9/8 info, contact information. 3. Invoices: Invoice data including invoice number, amount, and payment status. | S2C | Phase 3
Supplier Relationship Management (SRM)
ERP-S2C-212 | The SRM Solution shall have a supplier self-service portal that provides the following functionality: 1. Initiate a request to be a supplier. 2. Update supplier information 3. See status of invoice payment, upcoming bid opportunities, submitted bids, awarded contracts/Pos 4. Mass communication. | S2C | Phase 3
ERP-S2C-213 | The SRM solution shall integrate with the ERP system to communicate data related to the following procurement elements: 1. Purchase Orders (POs): Detailed information regarding purchase orders, including PO number, supplier details, and status. 2. Supplier/vendor Details: Payment terms, W9/8 info, contact information. 3. Invoices: Invoice data including invoice number, amount, and payment status. | S2C | Phase 3
ERP-S2C-214 | The SRM Solution shall have a Suppler Evaluation or Score card function with multiple templates for different types of Projects or types of suppliers. Ie. Road Construction contractors require a much more rigorous evaluation compared to a retail supplier of goods compared to a consultant the provides business consultation services. | S2C | Phase 3
ERP-S2C-215 | The SRM solution shall be integrated with external databases to verify or retrieve date such as: 1. XBE (business owned by recognized minorities, women, veterans, or socially disadvantaged persons). Certifying agencies like Indiana Dept of Admin (IDOA), Indiana Department of Transportation (INDOT), Women's Business Enterprise Council (WBENC), Nationally Minority Supplier Development Council (NMSDC). 2. United Nations Standard Products and Services Code (UNSPSC) and North American Industry Classification System (NAICS). 3. Recognized ratings from the three major credit ratings (Standard & Poor’s, Moody's, and Fitch). | S2C | Phase 3
Strategic Sourcing
ERP-S2C-216 | The S2C Solution shall all authorized users to create a request for a strategic sourcing event to include but not limited to: 1. Budget 2. Statement of Work for services and materials 3. recommended suppliers/contractors | S2C | Phase 3
ERP-S2C-217 | The S2C solution shall integrate with the ERP system to communicate data related to the following procurement elements: 1. Purchase Orders (POs): Detailed information regarding purchase orders, including PO number, supplier details, and status. 2. Supplier/vendor Details: Payment terms, W9/8 info, contact information. 3. Invoices: Invoice data including invoice number, amount, and payment status. | S2C | Phase 3
ERP-S2C-218 | The S2C Solution shall have multiple templates for different types of Sourcing events. | S2C | Phase 3
ERP-S2C-219 | The S2C solution shall be able to post a letting list publicly, collect and evaluate bids | S2C | Phase 3
Time Sheet
ITR-TS-001 | The solution shall automatically import active projects, along with their corresponding stakeholders and project team members, from the PMO project database by integrating with the PMO Solution. Alternatively, the solution shall allow an Administrator to manually export and upload this data. | Administrator | Phase 3
ITR-TS-002 | The Solution shall allow Administrator to add non-PMO projects along with their corresponding stakeholders and project team members. | Administrator | Phase 3
ITR-TS-003 | The Solution shall allow ITR employees and authorized third-party personnel to log hours for the project(s) they are assigned to. This logging can be daily and/or weekly, one time or multiple times. | ITR Employee & Third-party personnel | Phase 3
ITR-TS-004 | The Solution shall allow ITR employees and authorized third-party personnel to save their time sheets as a draft before submission. | ITR Employee & Third-party personnel | Phase 3
ITR-TS-005 | The Solution shall allow ITR employees and third-party personnel to submit their timesheet daily, weekly, or monthly for review and approval. | ITR Employee & Third-party personnel | Phase 3
ITR-TS-006 | The Solution shall allow ITR employees and authorized third-party personnel to clone their submitted timesheet for the following week with an option to make any changes. | ITR Employee & Third-party personnel | Phase 3
ITR-TS-007 | The Solution shall allow ITR employees and third-party personnel to view the previously submitted timesheets. | ITR Employee & Third-party personnel | Phase 3
ITR-TS-008 | Upon submission of an employee’s timesheet, the Solution shall automatically generate project-specific timesheets for each project the employees logged hours against. | Time Reporting Solution | Phase 3
ITR-TS-009 | Upon project-specific timesheet generation, the Solution shall notify Project Manager to review and approve/reject the timesheet entries submitted. The notification must include, but not limited to, employee name, project name, day, week or month. | Time Reporting Solution | Phase 3
ITR-TS-010 | The Solution shall allow Project Manager to review, approve, or reject submitted timesheets with the option to send a customized Boolean text message. | Project Manager | Phase 3
ITR-TS-011 | The Solution shall allow Project Manager to generate an ad hoc report detailing the hours spent on one or more projects assigned to them (grouped by size of the project) with the ability to specify a start date and an end date in the format (MM-DD-YYYY), with built-in validation to ensure the date format is correct and that the start date is earlier than or equal to the end date. Additionally, the report shall be exportable in common formats, including PDF, CSV, and Excel. | Project Manager | Phase 3
ITR-TS-012 | The Solution shall allow PMO Director and ExCo Member to generate an ad hoc report detailing the hours spent on all projects (grouped by department, project size, or both)in the portfolio with the ability to specify a start date and an end date in the format (MM-DD-YYYY), with built-in validation to ensure the date format is correct and that the start date is earlier than or equal to the end date. Additionally, the report shall be exportable in common formats, including PDF, CSV, and Excel. | PMO Director | Phase 3
ExCo Member
ITR-TS-013 | The Solution shall allow Departmental Director and Manager to generate an ad hoc report detailing the hours spent on all projects withing the department (grouped by project size) with the ability to specify a start date and an end date in the format (MM-DD-YYYY), with built-in validation to ensure the date format is correct and that the start date is earlier than or equal to the end date. Additionally, the report shall be exportable in common formats, including PDF, CSV, and Excel. | Departmental Director/ | Phase 3
Manager
ITR-TS-014 | The solution shall allow ExCo Members, Department Directors, and Managers to log Out-of-Office (OOO) time on behalf of their subordinates and automatically prevent those subordinates from logging work hours during the specified OOO periods. | ExCo Member | Phase 3
Departmental Director/Manager
ITR-TS-015 | The solution shall allow Finance Representatives to generate and extract a monthly report summarizing hours spent across all projects for a selected month or a range of multiple months, categorized by hours worked by salaried employees and hourly employees. | Finance Representatives | Phase 3
ITR-TS-016 | The solution shall allow HR Representatives to generate and extract a monthly report summarizing hours spent across all projects for a selected week or a range of multiple weeks, categorized by hours worked by salaried employees and hourly employees. | HR Representatives | Phase 3
ITR-TS-017 | The Solution shall allow the Administrator to configure the working days, hours, and holidays. | Administrator | Phase 3
ITR-TS-018 | The Solution shall allow Administrator to configure notification settings for timesheet-related events. The configuration shall include (but is not limited to) the following: | Administrator | Phase 3
Reminders:
Automatic reminders for timesheet submission on the last working day of the week and the last working day of the month.
Approval Overdue Notifications:
Automatic notifications to the assigned project manager if a timesheet approval is overdue. The criteria for overdue approval (e.g., X days after submission) shall be configurable.
Overdue Submission Alerts:
Configurable parameters that define the allowable number of days for timesheet submission. If timesheets are not submitted within the configured timeframe, the solution shall send an alert to the respective employees and, optionally, to a designated manager and project manager.
Notification Delivery:
Support for configuring the notification delivery method (e.g., email, in-app alerts) and scheduling the time of day when notifications are sent.
ITR-TS-019 | The Solution shall log all notification events, including the type of notification, the recipient, and the time sent, to support auditing and troubleshooting. | Time Reporting Solution | Phase 3
ITR-TS-020 | The solution shall allow Supervisors to log hours, submit timesheets, and make edits to timesheets on behalf of their temporary and seasonal employees. | Supervisor | Phase 3
ITR-TS-021 | The solution shall have project codes, tasks and phase codes that define the project, task and type of work being done. Type of work can be planning, design, development, testing installation, construction, training, or other configurable phases. | Time Reporting Solution | Phase 3
ITR-TS-022 | The Solution shall allow a Company authorized staff member to set up new users, modify employee status and set start and end dates. | Time Reporting Solution | Phase 3
ITR-TS-023 | The Solution shall retain all employees by name and unique ID number with effective start and end dates. Employees shall be turned on or off and all data shall be retained in accordance with the data retention requirements. | Time Reporting Solution | Phase 3
ITR-TS-024 | The Solution shall support 100 concurrent users logged in and at least 10,000 named users. | Time Reporting Solution | Phase 3