## Question Log
SB West over US 31 Construction
IFB Page Number/ Plan Sheet Page Number | Bidder question | Initals | Date | ITRCC/Design Team Response | Initals | Date
| Is this Job going to bid as a Lump Sum? If not, can ITRCC put out bid proposal? If yes, how is quantity changes going to be addressed? | MZ | 2026-06-08 | Please see attached itemized list. The bid is still lump sum (please submit bid with Schedule of Values listed in IFB), and quantities will be tracked and paid accordingly. Anything that will require us to go over the lump sum price will require a change order. Work is not to be done unless there is approval in a change order. | AT | 2026-06-08
1 | On sheet 1 (Cover sheet) It appears you have the structure locations incorrect. Locations shown for 06792 and OWX-1 should be flipped. Please clarify | PLR | 2026-06-11 | Sheet 1 (Cover sheet) corrected as indicated | SCD | 2026-06-12
??? | Need more information as to what is expected for the Police Ramp removal. 1. Dimensions (length & width)? 2. To what depth? 3. Are actually removing anyting or are we just milling up in place, leaving the spoils as quasi shoulder material? | PLR | 2026-06-15
??? | On the Item Sheet, Pavement Removal is listed at 3,782 sys. Where is all this quantity? Outside of the 156 sys for Str. 031-71-06792, is the rest of the quantity for the Police Ramp removal? | PLR | 2026-06-15
??? | The schedule of values includes ITRCC Item 3 for a polyester polymer concrete overlay. Please add items to the item list for this alternate bid. Or should this alternate be removed? | JK | 2026-06-15
??? | Are items 6 and 7 of the schedule of values LS units? | JK | 2026-06-15